## Dashboard
NyrA Launch Command Center
Launch Verdict | NO-GO public paid launch
Paid Beta Path | Possible after P0 gates
P0 Tasks
Blocked Tasks
Low Cash Estimate
Prudent Cash Estimate
Last Rebuilt | 2026-07-18 09:47
Top Next Actions
Task | Lane | Owner | Priority | Status | Detail
Business name search | Legal/Business | User | P0 | Not started | Search SC business filings and USPTO for NyrA/Nyra Swarm/NyrA Little Buddy conflicts
Choose entity path | Legal/Business | User | P0 | SC LLC selected | SC LLC path saved as Porter Labs LLC in command center; formation evidence uploaded and filing remains in progress
File SC LLC if chosen | Legal/Business | User | P0 | In progress | Porter Labs LLC SC registration is in progress via uploaded ZenBusiness evidence; formation date still not issued
Get EIN | Legal/Business | User | P0 | Blocked on formation | Apply through IRS after the LLC formation date is issued; current evidence shows EIN not started
Open/confirm business bank | Finance | User | P0 | Blocked on entity/EIN | Separate revenue from personal money
Stripe identity/tax setup | Payments | User | P0 | Waiting on tax/pricing | Use Porter Labs LLC and porterlabz.com for Stripe identity after tax decision, price, portal, and legal review clear
Choose monthly price | Payments | User | P0 | Open | Pick first monthly SKU price using the Pricing Model page; model currently supports a $25 planning scenario with payment/provider/support reserves, but final price needs user approval
Choose hosted AI cap | Payments/Product | User | P0 | Open | Define included usage and over-cap behavior using the Pricing Model page; model currently calculates a hosted-message cap from token and margin assumptions because BYOK is later
Pricing and hosted AI cap model | Payments/Product | Codex | P0 | Ready | Pricing model script docs snapshot CSV and command-center Pricing page estimate Stripe fees provider token cost support/infra/refund reserves target margin minimum price and recommended hosted AI cap
Create Stripe product/price | Payments | Codex | P0 | Ready | Use billing:stripe-setup after price and Stripe key are ready

## Command Brief
Type | Priority | Owner | Lane | Title | Status | Action | DashboardPage | DashboardField | UploadSlot
User Handoff | P0 | User | Business Legal | Attorney/accountant review approved for paid beta | Waiting on user | Mark Approved only after attorney/accountant review clears paid beta. | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | legal-review
User Handoff | P0 | User + Codex | Payments Licensing | Billing rehearsal mode set to live for final money preflight | Waiting on user | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass. | pages/billing-rehearsal.html | billingRehearsal.mode | stripe-screenshots
User Handoff | P0 | User + Codex | Release Ops | Paid beta installer is signed or store-trusted | Waiting on user | Upload or generate signed/store-trusted release evidence after the signing path is chosen. | pages/release-package.html | releasePackage.signingStatus | code-signing
Deployability Blocker | P0 | User | Business Legal | Attorney/accountant review approved for paid beta | Waiting on user | Mark Approved only after attorney/accountant review clears paid beta. | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | legal-review
Deployability Blocker | P0 | User + Codex | Payments Licensing | Billing rehearsal mode set to live for final money preflight | User + Codex gated | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass. | pages/billing-rehearsal.html | billingRehearsal.mode | stripe-screenshots
Deployability Blocker | P0 | User + Codex | Release Ops | Paid beta installer is signed or store-trusted | User + Codex gated | Upload or generate signed/store-trusted release evidence after the signing path is chosen. | pages/release-package.html | releasePackage.signingStatus | code-signing
Deployability Blocker | P1 | Codex | Visual Assets | Launch visuals use current shipping app screenshots | Codex queued | Capture and approve current product screenshots after the shipping UI and billing/support flows are final. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Secret Setup | P0 | User | Stripe Billing | STRIPE_SECRET_KEY | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell. Setup command placeholder: npx wrangler secret put STRIPE_SECRET_KEY --cwd cloud/billing-worker --env production ¦ $env:STRIPE_SECRET_KEY = "<STRIPE_SECRET_KEY>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: STRIPE_SECRET_KEY | cloud-handoff
Secret Setup | P0 | User | Stripe Billing | STRIPE_WEBHOOK_SECRET | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell. Setup command placeholder: npx wrangler secret put STRIPE_WEBHOOK_SECRET --cwd cloud/billing-worker --env production ¦ $env:STRIPE_WEBHOOK_SECRET = "<STRIPE_WEBHOOK_SECRET>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: STRIPE_WEBHOOK_SECRET | cloud-handoff
Secret Setup | P0 | User | Stripe Billing | NYRA_STRIPE_PRICE_PRO_MONTHLY | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell. Setup command placeholder: npx wrangler secret put NYRA_STRIPE_PRICE_PRO_MONTHLY --cwd cloud/billing-worker --env production ¦ $env:NYRA_STRIPE_PRICE_PRO_MONTHLY = "<NYRA_STRIPE_PRICE_PRO_MONTHLY>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_STRIPE_PRICE_PRO_MONTHLY | cloud-handoff
Secret Setup | P0 | User | NyrA Billing | NYRA_BILLING_SUCCESS_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable. Setup command placeholder: npx wrangler secret put NYRA_BILLING_SUCCESS_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_SUCCESS_URL = "<NYRA_BILLING_SUCCESS_URL>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_SUCCESS_URL | cloud-handoff
Secret Setup | P0 | User | NyrA Billing | NYRA_BILLING_CANCEL_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable. Setup command placeholder: npx wrangler secret put NYRA_BILLING_CANCEL_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_CANCEL_URL = "<NYRA_BILLING_CANCEL_URL>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_CANCEL_URL | cloud-handoff
Secret Setup | P0 | User | NyrA Billing | NYRA_BILLING_RETURN_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable. Setup command placeholder: npx wrangler secret put NYRA_BILLING_RETURN_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_RETURN_URL = "<NYRA_BILLING_RETURN_URL>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_RETURN_URL | cloud-handoff
Secret Setup | P0 | User | NyrA License | NYRA_LICENSE_API_TOKEN | Secret-store only | Cloudflare billing Worker secret and desktop activation configuration. Setup command placeholder: npx wrangler secret put NYRA_LICENSE_API_TOKEN --cwd cloud/billing-worker --env production ¦ $env:NYRA_LICENSE_API_TOKEN = "<NYRA_LICENSE_API_TOKEN>". Verify with npm run cloud:billing:check && npm run test:cloud-billing-worker. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_API_TOKEN | cloud-handoff
Secret Setup | P0 | User | NyrA License | NYRA_LICENSE_SIGNING_SECRET | Secret-store only | Cloudflare billing Worker and mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/billing-worker --env production ¦ npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/mobile-bridge-worker --env production. Verify with npm run cloud:billing:check && npm run test:cloud-billing-worker && npm run cloud:mobile-bridge:check. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_SIGNING_SECRET | cloud-handoff
Secret Setup | P0 | User | NyrA Mobile Bridge | NYRA_MOBILE_BRIDGE_TOKEN | Secret-store only | Cloudflare mobile bridge Worker secret and temporary bridge test shell. Setup command placeholder: npx wrangler secret put NYRA_MOBILE_BRIDGE_TOKEN --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_MOBILE_BRIDGE_TOKEN = "<NYRA_MOBILE_BRIDGE_TOKEN>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_MOBILE_BRIDGE_TOKEN | cloud-handoff
Secret Setup | P1 | User | NyrA Mobile Bridge | NYRA_OPENAI_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_OPENAI_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_OPENAI_API_KEY = "<NYRA_OPENAI_API_KEY>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_OPENAI_API_KEY | cloud-handoff
Secret Setup | P1 | User | NyrA Mobile Bridge | NYRA_ANTHROPIC_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_ANTHROPIC_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_ANTHROPIC_API_KEY = "<NYRA_ANTHROPIC_API_KEY>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_ANTHROPIC_API_KEY | cloud-handoff
Secret Setup | P1 | User | NyrA Mobile Bridge | NYRA_GEMINI_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_GEMINI_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_GEMINI_API_KEY = "<NYRA_GEMINI_API_KEY>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_GEMINI_API_KEY | cloud-handoff
Secret Setup | P1 | User | NyrA Mobile Bridge | NYRA_GROK_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_GROK_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_GROK_API_KEY = "<NYRA_GROK_API_KEY>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_GROK_API_KEY | cloud-handoff
Secret Setup | P1 | User | NyrA Mobile Bridge | NYRA_ANDROID_DOWNLOAD_TICKET_SECRET | Secret-store only | Cloudflare mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_ANDROID_DOWNLOAD_TICKET_SECRET --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_ANDROID_DOWNLOAD_TICKET_SECRET = "<NYRA_ANDROID_DOWNLOAD_TICKET_SECRET>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_ANDROID_DOWNLOAD_TICKET_SECRET | cloud-handoff
Secret Setup | P1 | User | Cloud Command Center | NYRA_COMMAND_TOKEN | Waiting on private token | Cloudflare command-center Worker secret. Setup command placeholder: npx wrangler secret put NYRA_COMMAND_TOKEN --cwd cloud/command-center-worker --env production. Verify with npm run cloud:command-center:health. | pages/cloud.html | deployment secret store: NYRA_COMMAND_TOKEN | cloud-handoff
Cloud Secret Setup | P1 | User + Codex | Cloud Command Center | NYRA_COMMAND_CENTER_API_URL | Waiting on deployed Worker URL | Temporary local shell and browser Cloud Connection URL field after Worker deployment. Setup command placeholder: $env:NYRA_COMMAND_CENTER_API_URL = "https://<your-command-center-worker-url>". Verify with npm run cloud:command-center:health. | pages/cloud.html | cloudSync.apiUrl | cloud-handoff
Cloud Secret Setup | P1 | User | Cloud Command Center | NYRA_COMMAND_CENTER_TOKEN | Waiting on temporary sync token | Temporary local shell and browser localStorage only. Setup command placeholder: $env:NYRA_COMMAND_CENTER_TOKEN = "<same private value as NYRA_COMMAND_TOKEN>". Verify with npm run cloud:command-center:health. | pages/cloud.html | browser localStorage only: nyraCommandCenterApiConfig.token | cloud-handoff
Cloud Bootstrap Pack | P0 | User | 1. Authentication | Cloudflare API token required | Ready | Create a scoped Cloudflare API token for the account that will host NyrA, set it as CLOUDFLARE_API_TOKEN in the local shell or automation secret store, then rerun npm run cloudflare:discover. | pages/cloud-bootstrap.html | cloudMigration.accountReady | cloud-handoff
Cloud Bootstrap Pack | P1 | User | 1. Authentication | Wrangler login | Ready | If you are sitting at the Windows desktop and prefer browser auth, run npx wrangler login and approve the Cloudflare account that will host NyrA. Automation still needs CLOUDFLARE_API_TOKEN. | pages/cloud-bootstrap.html | cloudMigration.accountReady | cloud-handoff
Cloud Bootstrap Pack | P0 | User + Codex | 2. Remote Resources | D1: nyra_command_center | Ready for config review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud.html | cloudMigration.d1DatabaseId | cloud-handoff
Cloud Bootstrap Pack | P0 | User + Codex | 2. Remote Resources | D1: nyra_billing | Ready for config review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud-billing.html | billingCloud.d1DatabaseId | cloud-handoff
Cloud Bootstrap Pack | P0 | User + Codex | 2. Remote Resources | R2: nyra-command-center-uploads | Ready for config review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud.html | cloudMigration.r2Bucket | cloud-handoff
Cloud Bootstrap Pack | P0 | User + Codex | 2. Remote Resources | R2: nyra-mobile-support-logs | Ready for config review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud-mobile-bridge.html | mobileBridge.r2BucketName | cloud-handoff
Cloud Bootstrap Pack | P1 | User + Codex | 2. Remote Resources | R2: nyra-android-releases | Ready for config review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud-mobile-bridge.html | mobileBridge.androidReleasesBucketName | cloud-handoff
Cloud Bootstrap Pack | P1 | User + Codex | 2. Remote Resources | Pages: nyra-command-center-dashboard | Ready for config review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud.html | cloudPages.projectName | cloud-handoff
Cloud Bootstrap Pack | P1 | Codex | 2. Remote Resources | Worker: nyra-command-center-api | Ready for deploy review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud.html | cloudSync.apiUrl | cloud-handoff
Cloud Bootstrap Pack | P1 | Codex | 2. Remote Resources | Worker: nyra-billing-api | Ready for deploy review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud-billing.html | billingCloud.workerUrl | cloud-handoff
Cloud Bootstrap Pack | P1 | Codex | 2. Remote Resources | Worker: nyra-mobile-bridge-api | Ready for deploy review | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | pages/cloud-mobile-bridge.html | mobileBridge.workerUrl | cloud-handoff
Cloud Bootstrap Pack | P0 | Codex | 3. Config Sync | sync non secret config | Waiting on prior gates | Apply saved non-secret dashboard values to production Worker configs and verify the mobile bridge bootstrap plan. | pages/cloud-bootstrap.html |  | cloud-handoff
Cloud Bootstrap Pack | P0 | User + Codex | 4. Secrets | command token secret | Waiting on prior gates | Set the private command-center API bearer token through Wrangler secrets only. | pages/cloud-bootstrap.html |  | cloud-handoff
Cloud Bootstrap Pack | P0 | User + Codex | 4. Secrets | billing secret stripe secret key | Waiting on prior gates | Set STRIPE_SECRET_KEY for the billing Worker through Wrangler secrets only. | pages/cloud-bootstrap.html |  | cloud-handoff
Cloud Deploy Pack | P1 | Codex | 5. First Cloud Sync | Cloud API URL available for sync | post-deploy | After Worker deployment, set NYRA_COMMAND_CENTER_API_URL in a temporary shell and the browser Cloud Connection URL field. | pages/cloud.html | cloudSync.apiUrl | cloud-handoff
Cloud Deploy Pack | P1 | Codex | 5. First Cloud Sync | Cloud API token available for sync | post-deploy | Set NYRA_COMMAND_CENTER_TOKEN in a temporary shell using the same private value as NYRA_COMMAND_TOKEN after the Worker secret is created. | pages/cloud.html | browser localStorage only: nyraCommandCenterApiConfig.token | cloud-handoff
Hosted Alpha | P1 | Codex | Mobile Bridge | Hosted alpha phone test stays green | Hosted Alpha Ready | Run npm run alpha:hosted:check before phone testing; 4/4 providers ready, APK 0.1.0-alpha.83, download hash matches manifest, support log readback passed (2026-07-17T04-53-44-939Z-4ef1c4c3-4c15-45d9-80ac-4a7365b366d2). | pages/cloud-mobile-bridge.html | mobileBridge.lastPhoneSelfTest | phone-evidence
Hosted Alpha | P0 | User + Codex | Payments Licensing | Prove customer checkout and device restore on 0.1.0-alpha.83 | Internal alpha only until a real customer checkout and device-restore roundtrip is proven, physical-phone proof passes, and signed/trusted distribution is ready. | Complete a Stripe test-mode checkout from a clean install, confirm webhook activation, pair a second install, and record the customer portal and restore evidence. | pages/billing-rehearsal.html | billingRehearsal.customerPortalConfigured | stripe-screenshots
Cloudflare Discovery | P0 | User + Codex | 4. Host Dashboard | Map and protect command-center domain | Waiting on Pages custom domain | Add command.porterlabz.com as a custom domain on the nyra-command-center-dashboard Pages project, verify DNS/SSL, and apply the selected private access policy before publishing current business records. | pages/cloud.html | cloudMigration.dashboardDomain | cloud-handoff
Cloudflare Discovery | P1 | Codex | 4. Verify | Refresh Cloudflare discovery | Open | Rerun discovery after any Cloudflare dashboard or Wrangler resource change so the command center stays current. | pages/cloudflare-discovery.html | cloudMigration.notes | cloud-handoff
Payment Launch Pack | P0 | User | 1. Legal And Stripe Identity | Attorney/accountant review approved for paid beta | Waiting on user | Mark attorney/accountant review approved only after paid-beta policies, tax, refund, privacy, and support language are cleared. | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | legal-review
Payment Launch Pack | P0 | User + Codex | 8. Live Payment Gate | Billing rehearsal mode set to live for final money preflight | User + Codex gated | Keep rehearsal mode in test until test checkout, portal, webhook, support, legal, domain, secrets, and release gates pass. | pages/billing-rehearsal.html | billingRehearsal.mode | stripe-screenshots
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | STRIPE_SECRET_KEY | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: STRIPE_SECRET_KEY | cloud-handoff
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | STRIPE_WEBHOOK_SECRET | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: STRIPE_WEBHOOK_SECRET | cloud-handoff
Payment Launch Pack | P0 | User | 3. Stripe Product And Price | NYRA_STRIPE_PRICE_PRO_MONTHLY | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_STRIPE_PRICE_PRO_MONTHLY | cloud-handoff
Payment Launch Pack | P0 | User | 6. Support And Domain | NYRA_BILLING_SUCCESS_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_SUCCESS_URL | cloud-handoff
Payment Launch Pack | P0 | User | 6. Support And Domain | NYRA_BILLING_CANCEL_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_CANCEL_URL | cloud-handoff
Payment Launch Pack | P0 | User | 6. Support And Domain | NYRA_BILLING_RETURN_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_RETURN_URL | cloud-handoff
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | NYRA_LICENSE_API_TOKEN | Secret-store only | Cloudflare billing Worker secret and desktop activation configuration; verify with npm run cloud:billing:check && npm run test:cloud-billing-worker. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_API_TOKEN | cloud-handoff
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | NYRA_LICENSE_SIGNING_SECRET | Secret-store only | Cloudflare billing Worker and mobile bridge Worker secret; verify with npm run cloud:billing:check && npm run test:cloud-billing-worker && npm run cloud:mobile-bridge:check. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_SIGNING_SECRET | cloud-handoff
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | NYRA_MOBILE_BRIDGE_TOKEN | Secret-store only | Cloudflare mobile bridge Worker secret and temporary bridge test shell; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_MOBILE_BRIDGE_TOKEN | cloud-handoff
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | NYRA_OPENAI_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_OPENAI_API_KEY | cloud-handoff
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | NYRA_ANTHROPIC_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_ANTHROPIC_API_KEY | cloud-handoff
Payment Launch Pack | P0 | User | 7. Secret Store And Rehearsal | NYRA_GEMINI_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_GEMINI_API_KEY | cloud-handoff
Release Trust Pack | P0 | User + Codex | 4. Signed Or Store Evidence | Paid beta installer is signed or store-trusted | User + Codex gated | Produce signed direct-download installer evidence or store-trusted package/listing evidence before any paid beta customer receives the build. | pages/release-package.html | releasePackage.signingStatus | code-signing
Release Trust Pack | P0 | User + Codex | 2. Signing Build Readiness | Windows signing readiness is proven | blocked | Finish Microsoft Artifact Signing or PFX handoffs so Codex can produce a signed Windows installer without storing secrets in the repo. | pages/release-package.html | windowsSigningReadiness.status | code-signing
Release Trust Pack | P0 | User + Codex | 4. Signed Or Store Evidence | Trusted installer evidence clears release candidate | blocked | Choose the release trust path and produce signed or store-trusted installer evidence before paid beta. | pages/release-package.html | releasePackage.signingStatus | code-signing
Version Control Pack | P0 | User | 2. Repository Baseline | GitHub remote or repo URL saved | Waiting on handoff | Save the intended GitHub repository owner/name or remote URL in the dashboard. | pages/version-control.html | versionControl.repoRemoteUrl | version-control
Version Control Pack | P0 | User + Codex | 2. Repository Baseline | GitHub repo creation or push path available | Waiting on handoff | Authenticate GitHub CLI or save an existing remote URL in the dashboard. | pages/version-control.html | versionControl.repoRemoteUrl | version-control
Version Control Pack | P0 | User + Codex | 2. Repository Baseline | Push dry-run readiness captured | Waiting on handoff | Save or configure the intended GitHub origin remote, then rerun the dry-run push check before any tag or signing handoff. | pages/version-control.html | versionControl.repoRemoteUrl | version-control
Public Launch Config | P0 | User | Business Legal | Business/legal name | Ready | Enter the business/legal name that will appear in Stripe, receipts, policies, and release metadata. | pages/collaboration.html | decisions.businessName
Public Launch Config | P0 | User | Cloud Platform | Public domain | Ready | Enter the public product/policy domain or subdomain. | pages/collaboration.html | decisions.domain
Public Launch Config | P0 | User | Support Ops | Support email | Ready | Confirm the support inbox that will appear on policy pages, Stripe receipts, and the launch site. | pages/support.html | decisions.supportEmail
Public Launch Config | P0 | User | Payments Licensing | Monthly price | Ready | Enter the approved monthly price in cents before creating the live Stripe Price. | pages/pricing.html | decisions.monthlyPriceCents
Public Launch Config | P0 | User | Payments Licensing | Hosted AI cap | Ready | Enter the customer-facing hosted AI usage cap before publishing pricing or checkout. | pages/pricing.html | decisions.hostedAiCap
Public Launch Config | P0 | User + Codex | Payments Licensing | Billing backend URL | Ready | Deploy or choose the hosted billing backend URL. If billingCloud.workerUrl is saved, this pack can mirror it into billingRehearsal.backendBaseUrl. | pages/billing-rehearsal.html | billingRehearsal.backendBaseUrl
Public Launch Config | P1 | User | Payments Licensing | Customer Portal configured | Ready | Mark Yes only after Customer Portal cancellation, invoices, and payment methods are enabled and tested. | pages/billing-rehearsal.html | billingRehearsal.customerPortalConfigured
Decision Recommendation | P0 | User | Business Legal | Business name candidate | Saved matches recommendation | Confirm the final legal/business name, save it in the dashboard, and upload sanitized filing evidence when available. | pages/collaboration.html | decisions.businessName
Decision Recommendation | P0 | User | Business Legal | Entity path | Saved matches recommendation | Choose SC LLC or another documented entity path, then save the decision and upload the filing or accountant/legal note. | pages/collaboration.html | decisions.entityPath
Decision Recommendation | P0 | User | Business Legal | Tax collection/accounting path | Saved matches recommendation | Choose Stripe Tax now, accountant first, or SC-only beta in the dashboard. Get accountant/legal review before live public charging. | pages/collaboration.html | decisions.taxDecision
Decision Recommendation | P0 | User | Payments Licensing | Monthly subscription price | Saved matches recommendation | Save the approved monthly price in cents before creating the Stripe Price. | pages/pricing.html | decisions.monthlyPriceCents
Decision Recommendation | P0 | User | Payments Licensing | Hosted AI cap | Saved matches recommendation | Save the customer-facing hosted AI cap and over-cap behavior before checkout copy is published. | pages/pricing.html | decisions.hostedAiCap
Decision Recommendation | P0 | User | Support Ops | Support inbox | Saved matches recommendation | Confirm you own the inbox, send a test ticket, reply, then mark billingRehearsal.supportInboxConfirmed as Yes. | pages/support.html | decisions.supportEmail
Decision Recommendation | P0 | User | Business Legal | Refund and cancellation policy | Suggested - not saved | Have the refund/cancellation language reviewed before paid launch and upload legal review evidence. | pages/refund-cancellation.html | policy.review.refundCancellation
Decision Recommendation | P0 | User + Codex | Payments Licensing | Billing entitlement storage host | Saved matches recommendation | Approve Cloudflare billing storage and paste the D1 database ID after creation. | pages/billing-rehearsal.html | billingDeployment.storageHostDecision
Decision Recommendation | P0 | User + Codex | Cloud Platform | Cloud command-center stack | Saved different value | Approve the Cloudflare account/domain/admin/access handoff so the dashboard can move off local files. | pages/cloud.html | cloudMigration.target
Decision Recommendation | P0 | User + Codex | Cloud Platform | Cloud access model | Saved matches recommendation | Choose Cloudflare Access plus private token, then save the access model and admin email. | pages/cloud.html | cloudMigration.accessDecision
Decision Recommendation | P0 | User | Release Ops | Release channel | Saved matches recommendation | Choose direct download beta, Microsoft Store, or both before release rehearsal. | pages/collaboration.html | decisions.releaseChannel
Decision Recommendation | P0 | User | Release Ops | Code-signing path | Saved matches recommendation | Choose Microsoft Trusted Signing, Microsoft Store first, OV certificate, or hold. Upload signing/store evidence before paid beta. | pages/collaboration.html | decisions.codeSigningDecision
Decision Recommendation | P1 | Codex | Release/Product | App version path | Saved different value | Use the App Version page to record any required mobile companion boundaries or app-store goals. | pages/app-version.html | appVersion.mobileCompanionBoundary
Decision Recommendation | P1 | Codex | Marketing Visuals | Shipping visuals | Suggested - not saved | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | pages/visuals.html | visualProduction.finalScreenshotsApproved
Collaboration Workspace | P1 | User + Codex | Command Center Intake | Daily Build Intake | Ready for Codex review | Run intake scan, handoff delta, daily brief, and agent dispatch; then continue the next unblocked NyrA build task. | pages/collaboration.html | intake.userDecisionSummary | qa-evidence
Collaboration Workspace | P1 | User | Business Legal | Business, LLC, Tax | Partially filled | Fill 1 required dashboard field, then save, scan, and route. | pages/collaboration.html | decisions.einStatus | llc-documents
Collaboration Workspace | P1 | User + Codex | Payments Licensing | Pricing, Stripe, Payments | Ready for Codex review | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets. | pages/collaboration.html | decisions.publicProductName | stripe-screenshots
Collaboration Workspace | P1 | User + Codex | Cloud Platform | Cloud Control Room | Ready for Codex review | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip. | pages/collaboration.html | decisions.cloudProvider | cloud-handoff
Collaboration Workspace | P1 | User + Codex | QA Release | App Version And Mobile | Ready for Codex review | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary. | pages/collaboration.html | appVersion.publisherName | code-signing
Collaboration Workspace | P1 | Codex + User approval | Marketing Visuals | Visual Production | Partially filled | Fill 1 required dashboard field, then save, scan, and route. | pages/collaboration.html | visualProduction.finalScreenshotsApproved | product-screenshots
Collaboration Workspace | P1 | User + Codex | Version Control | Version Control And Release History | Partially filled | Fill 1 required dashboard field, then save, scan, and route. | pages/collaboration.html | versionControl.repoRemoteUrl | version-control
Collaboration Workspace | P1 | User + Codex | Support Ops | Support, Policies, Public Web | Partially filled | Fill 1 required dashboard field, then save, scan, and route. | pages/collaboration.html | billingRehearsal.attorneyReviewStatus | domain-email
Collaboration Workspace | P1 | Codex | Agent Dispatch | Automation Loop | Tracking | Keep the command center, daily brief, agent dispatch pack, and build queues current until paid launch gates clear. | pages/collaboration.html | intake.requestedNextBuild | qa-evidence
Collaboration Handoff Card | P0 | User | Business Legal | Attorney/accountant review approved for paid beta | Waiting on user | Mark Approved only after attorney/accountant review clears paid beta. | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | legal-review
Collaboration Handoff Card | P0 | User + Codex | Payments Licensing | Billing rehearsal mode set to live for final money preflight | User + Codex gated | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass. | pages/billing-rehearsal.html | billingRehearsal.mode | stripe-screenshots
Collaboration Handoff Card | P0 | User + Codex | Release Ops | Paid beta installer is signed or store-trusted | User + Codex gated | Upload or generate signed/store-trusted release evidence after the signing path is chosen. | pages/release-package.html | releasePackage.signingStatus | code-signing
Visual Production Pack | P0 | Codex | 5. Other Visual Evidence | Android alpha83 responsive Command surface | Blocked | Refresh after each mobile Command surface or autonomous-run layout change. | pages/visuals.html | visualProduction.notes | product-screenshots
Visual Production Pack | P0 | User + Codex | 3. Billing Portal Capture | Customer Portal screen | Blocked | After Stripe Customer Portal is configured, capture the real customer portal screen and attach sanitized evidence to the dashboard. | pages/visuals.html | billingRehearsal.customerPortalConfigured | stripe-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Desktop Alpha83 answer-first response | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Idle NyrA buddy | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Right-click command menu | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Live voice controls | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Wake-gated pause/listening behavior | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Single buddy with right-click chat panel | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Screen-look permission state | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Camera permission state | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Computer-control active state | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Stop button / interruption evidence | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Android floating buddy over launcher | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. Current evidence is 0.1.0-alpha.80; shipping app is 0.1.0-alpha.83. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Visual Production Pack | P1 | Codex | 1. Refresh Shipping Screenshot | Android foreground panel and answer-first swarm state | Refresh required | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. Current evidence is 0.1.0-alpha.80; shipping app is 0.1.0-alpha.83. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots
Codex Work | P0 | Codex | Release | Windows installer version | Active | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear
Codex Work | P1 | Codex | Marketing | Demo video | Active | Storyboards shot lists captions recording checklist and demo/ad scenes now exist; final recording waits for final UI pricing billing support policy URLs and screenshots
Codex Work | P0 | Codex | Product Program | Daily command-center intake | Active | Automation inventory now verifies required NyrA Codex automations are real and active; daily agents read the Today Command Brief, Decision Recommendations, Handoff Routing Rehearsal, Handoff Action Pack, Agent Dispatch Pack, Dashboard and Collaboration answers, uploads, notes, handoff readiness, deployability blockers, release-candidate status, cloud state, marketing kit, visual status, route newly cleared work, and keep Cloudflare discovery limited to real config drift instead of already-saved D1/R2 handoffs
Verified Codex Gate | P0 | Codex | Payments/Product | Pricing and hosted AI cap model | Ready | Pricing model script docs snapshot CSV and command-center Pricing page estimate Stripe fees provider token cost support/infra/refund reserves target margin minimum price and recommended hosted AI cap
Verified Codex Gate | P0 | Codex | Payments | Create Stripe product/price | Ready | Use billing:stripe-setup after price and Stripe key are ready
Verified Codex Gate | P0 | Codex | Payments/QA | Billing live rehearsal | Ready | Guarded preflight and rehearsal scripts plus command-center Billing Rehearsal page now check Stripe key mode, required webhook events, Customer Portal/support/legal blockers, HTTPS URLs, no repo secrets, and live-mode safety flag before checkout is exposed
Verified Codex Gate | P0 | Codex | Payments/QA | Payment Launch Pack | Ready | Payment Launch Pack now generates JSON CSV Markdown dashboard workbook Today Brief queue Stripe product/price setup sequence Customer Portal/webhook/backend/secret-store actions test rehearsal commands and live-payment no-go rules
Verified Codex Gate | P0 | Codex | Engineering | Deploy billing backend | Ready | Standalone Node 24 billing backend deploy pack and Cloudflare Worker/D1 billing path are ready with manifests checklists health checks required secret lists route coverage storage probes entitlement writes idempotent webhook handling and test:billing-deploy/test:billing-storage/cloud:billing:check/test:cloud-billing-worker; actual hosted deployment still needs domain host or Worker URL D1 database ID secrets Stripe webhook Customer Portal price hosted AI cap support inbox and persistent managed storage
Verified Codex Gate | P0 | Codex | Payments/Cloud | Cloud billing Worker/D1 | Ready | Cloudflare Worker nyra-billing-api implements Stripe-hosted Checkout Customer Portal webhooks license status checkout-session claim device-scoped access tokens D1 entitlement/customer/event/device storage and local route tests; live use still needs Cloudflare account D1 database ID Worker URL Stripe test/live secrets price webhook endpoint support email legal URLs and dashboard origin
Release Candidate | P0 | User + Codex |  | Windows signing inputs are ready for a trusted installer build | blocked | Windows signing readiness is Microsoft Artifact Signing Handoffs Missing. Run npm run release:windows-signing:preflight, then finish the listed Microsoft Artifact Signing or PFX handoffs before building a paid beta installer.
Release Candidate | P0 | User + Codex |  | Paid beta installer is signed or store-trusted | blocked | Choose the release trust path and produce signed or store-trusted installer evidence before paid beta.
Release Candidate | P0 | User + Codex |  | Deployability preflight has no P0 blockers | blocked | 3 P0 deployability blockers remain. Use the Deployability page and Handoffs page before live money.
Release Candidate | P0 | User |  | Dashboard handoffs are cleared | blocked | 3 user handoffs and 0 secret-store handoffs are still waiting.
Release Candidate | P1 | User + Codex |  | Marketing campaign has final publish values | blocked | Final publication still needs Attorney/accountant review approval for paid beta; Final screenshots approved from the shipping build; Recorded 90-second product demo and 30-second ad using final screenshots and launch values.
Release Candidate | P1 | Codex |  | Visuals match the shipping app | blocked | Final screenshots, diagrams, and demo visuals must match the shipping app before paid beta marketing.
Release Candidate | P1 | User + Codex |  | Billing live rehearsal inputs are ready | blocked | After the legal and release-trust gates clear, switch rehearsal mode to live and run the guarded final preflight.
Release Candidate | P1 | User |  | Support and legal review are ready | blocked | Complete attorney/accountant review for the paid beta.
Cloud Handoff | P0 | Codex |  | Cloud API URL available for sync | post-deploy | After deploy, set NYRA_COMMAND_CENTER_API_URL in a temporary shell before cloud sync.
Cloud Handoff | P0 | Codex |  | Cloud API token available for sync | post-deploy | After deploy, set NYRA_COMMAND_CENTER_TOKEN in a temporary shell only; never write it to repo files.
Visual Work | P1 | Codex | Visual Assets | Final shipping screenshots and demo assets | Visuals In Progress | Storyboards and shot lists are ready; product demo and ad videos wait for final UI, pricing, billing, support, policy URLs, and screenshots.

## Handoff Pack
Phase | Severity | Lane | Owner | Readiness | Requirement | UserAction | EvidenceNeeded | DashboardPage | DashboardField | UploadSlot | CodexAfter | NoGoRule
1. Business Identity | P0 | Business Legal | User | Waiting on user | Attorney/accountant review approved for paid beta | Mark Approved only after attorney/accountant review clears paid beta. | save billingRehearsal.attorneyReviewStatus; Upload evidence to legal-review if there is a document, screenshot, receipt, or confirmation that proves it. | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | legal-review | Refresh policies, Stripe identity notes, support docs, release publisher metadata, and deployability preflight after the decision/evidence is saved. | Do not mark this cleared until the dashboard field or upload evidence proves it.
3. Billing And Stripe | P0 | Payments Licensing | User + Codex | Waiting on user | Billing rehearsal mode set to live for final money preflight | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass. | save billingRehearsal.mode; Upload evidence to stripe-screenshots if there is a document, screenshot, receipt, or confirmation that proves it. | pages/billing-rehearsal.html | billingRehearsal.mode | stripe-screenshots | Run billing and cloud billing checks, rehearse checkout/portal/webhooks in test mode, and keep live checkout disabled until all P0 gates close. | Do not mark this cleared until the dashboard field or upload evidence proves it.
6. Release Trust | P0 | Release Ops | User + Codex | Waiting on user | Paid beta installer is signed or store-trusted | Upload or generate signed/store-trusted release evidence after the signing path is chosen. | save releasePackage.signingStatus; Upload evidence to code-signing if there is a document, screenshot, receipt, or confirmation that proves it. | pages/release-package.html | releasePackage.signingStatus | code-signing | Enable the selected signed/store-trusted path, regenerate release evidence, and keep paid beta blocked until installer trust is proven. | Do not mark this cleared until the dashboard field or upload evidence proves it.

## Secret Store
VariableName | Service | Target | RequiredFor | SafeSetupCommands | VerificationCommand | NoGoRule | DashboardPage | DashboardField | UploadSlot
STRIPE_SECRET_KEY | Stripe Billing | Cloudflare billing Worker secret and temporary billing rehearsal shell | Stripe Checkout, Customer Portal, subscription lookups, and billing API requests. | npx wrangler secret put STRIPE_SECRET_KEY --cwd cloud/billing-worker --env production ¦ $env:STRIPE_SECRET_KEY = "<STRIPE_SECRET_KEY>" | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: STRIPE_SECRET_KEY | cloud-handoff
STRIPE_WEBHOOK_SECRET | Stripe Billing | Cloudflare billing Worker secret and temporary billing rehearsal shell | Stripe webhook signature verification for subscription and entitlement events. | npx wrangler secret put STRIPE_WEBHOOK_SECRET --cwd cloud/billing-worker --env production ¦ $env:STRIPE_WEBHOOK_SECRET = "<STRIPE_WEBHOOK_SECRET>" | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: STRIPE_WEBHOOK_SECRET | cloud-handoff
NYRA_STRIPE_PRICE_PRO_MONTHLY | Stripe Billing | Cloudflare billing Worker secret and temporary billing rehearsal shell | Checkout Session creation for the monthly Pro subscription price. | npx wrangler secret put NYRA_STRIPE_PRICE_PRO_MONTHLY --cwd cloud/billing-worker --env production ¦ $env:NYRA_STRIPE_PRICE_PRO_MONTHLY = "<NYRA_STRIPE_PRICE_PRO_MONTHLY>" | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: NYRA_STRIPE_PRICE_PRO_MONTHLY | cloud-handoff
NYRA_BILLING_SUCCESS_URL | NyrA Billing | Cloudflare billing Worker secret or hosted backend environment variable | Checkout success redirect after Stripe payment. | npx wrangler secret put NYRA_BILLING_SUCCESS_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_SUCCESS_URL = "<NYRA_BILLING_SUCCESS_URL>" | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_SUCCESS_URL | cloud-handoff
NYRA_BILLING_CANCEL_URL | NyrA Billing | Cloudflare billing Worker secret or hosted backend environment variable | Checkout cancellation redirect back to the launch or app flow. | npx wrangler secret put NYRA_BILLING_CANCEL_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_CANCEL_URL = "<NYRA_BILLING_CANCEL_URL>" | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_CANCEL_URL | cloud-handoff
NYRA_BILLING_RETURN_URL | NyrA Billing | Cloudflare billing Worker secret or hosted backend environment variable | Customer Portal return redirect after subscription management. | npx wrangler secret put NYRA_BILLING_RETURN_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_RETURN_URL = "<NYRA_BILLING_RETURN_URL>" | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_RETURN_URL | cloud-handoff
NYRA_LICENSE_API_TOKEN | NyrA License | Cloudflare billing Worker secret and desktop activation configuration | Private license status API access and customer-safe device activation. | npx wrangler secret put NYRA_LICENSE_API_TOKEN --cwd cloud/billing-worker --env production ¦ $env:NYRA_LICENSE_API_TOKEN = "<NYRA_LICENSE_API_TOKEN>" | npm run cloud:billing:check && npm run test:cloud-billing-worker | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_API_TOKEN | cloud-handoff
NYRA_LICENSE_SIGNING_SECRET | NyrA License | Cloudflare billing Worker and mobile bridge Worker secret | HMAC signing of device-scoped license access tokens accepted by billing and mobile bridge APIs. | npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/billing-worker --env production ¦ npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_LICENSE_SIGNING_SECRET = "<NYRA_LICENSE_SIGNING_SECRET>" | npm run cloud:billing:check && npm run test:cloud-billing-worker && npm run cloud:mobile-bridge:check | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_SIGNING_SECRET | cloud-handoff
NYRA_MOBILE_BRIDGE_TOKEN | NyrA Mobile Bridge | Cloudflare mobile bridge Worker secret and temporary bridge test shell | Private mobile bridge API authentication until paid customer auth replaces the bundled alpha-token path. | npx wrangler secret put NYRA_MOBILE_BRIDGE_TOKEN --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_MOBILE_BRIDGE_TOKEN = "<NYRA_MOBILE_BRIDGE_TOKEN>" | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_MOBILE_BRIDGE_TOKEN | cloud-handoff
NYRA_OPENAI_API_KEY | NyrA Mobile Bridge | Cloudflare mobile bridge Worker secret | Hosted OpenAI model routing through the mobile bridge. | npx wrangler secret put NYRA_OPENAI_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_OPENAI_API_KEY = "<NYRA_OPENAI_API_KEY>" | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_OPENAI_API_KEY | cloud-handoff
NYRA_ANTHROPIC_API_KEY | NyrA Mobile Bridge | Cloudflare mobile bridge Worker secret | Hosted Anthropic model routing through the mobile bridge. | npx wrangler secret put NYRA_ANTHROPIC_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_ANTHROPIC_API_KEY = "<NYRA_ANTHROPIC_API_KEY>" | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_ANTHROPIC_API_KEY | cloud-handoff
NYRA_GEMINI_API_KEY | NyrA Mobile Bridge | Cloudflare mobile bridge Worker secret | Hosted Gemini model routing through the mobile bridge. | npx wrangler secret put NYRA_GEMINI_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_GEMINI_API_KEY = "<NYRA_GEMINI_API_KEY>" | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_GEMINI_API_KEY | cloud-handoff
NYRA_GROK_API_KEY | NyrA Mobile Bridge | Cloudflare mobile bridge Worker secret | Hosted Grok model routing through the mobile bridge. | npx wrangler secret put NYRA_GROK_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_GROK_API_KEY = "<NYRA_GROK_API_KEY>" | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_GROK_API_KEY | cloud-handoff
NYRA_ANDROID_DOWNLOAD_TICKET_SECRET | NyrA Mobile Bridge | Cloudflare mobile bridge Worker secret | Short-lived Android APK download tickets for customer update installs without a bundled shared bridge token. | npx wrangler secret put NYRA_ANDROID_DOWNLOAD_TICKET_SECRET --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_ANDROID_DOWNLOAD_TICKET_SECRET = "<NYRA_ANDROID_DOWNLOAD_TICKET_SECRET>" | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_ANDROID_DOWNLOAD_TICKET_SECRET | cloud-handoff
NYRA_COMMAND_TOKEN | Cloud Command Center | Cloudflare command-center Worker secret | Bearer-token authentication on the deployed command-center API. Use the same private value in the local NYRA_COMMAND_CENTER_TOKEN shell variable when syncing. | npx wrangler secret put NYRA_COMMAND_TOKEN --cwd cloud/command-center-worker --env production | npm run cloud:command-center:health | Never place the command-center bearer token into wrangler.jsonc, dashboard state, repo files, screenshots, or chat. | pages/cloud.html | deployment secret store: NYRA_COMMAND_TOKEN | cloud-handoff
NYRA_COMMAND_CENTER_API_URL | Cloud Command Center | Temporary local shell and browser Cloud Connection URL field after Worker deployment | After deploy, set NYRA_COMMAND_CENTER_API_URL in a temporary shell before cloud sync. | $env:NYRA_COMMAND_CENTER_API_URL = "https://<your-command-center-worker-url>" | npm run cloud:command-center:health | Never publish a private dashboard URL without Cloudflare Access or bearer-token auth. The Worker URL itself can be saved in the dashboard. | pages/cloud.html | cloudSync.apiUrl | cloud-handoff
NYRA_COMMAND_CENTER_TOKEN | Cloud Command Center | Temporary local shell and browser localStorage only | CLI cloud sync and browser API calls after deployment. | $env:NYRA_COMMAND_CENTER_TOKEN = "<same private value as NYRA_COMMAND_TOKEN>" | npm run cloud:command-center:health | Store this only in the current shell or browser Cloud Connection control; clear it after use and never commit it. | pages/cloud.html | browser localStorage only: nyraCommandCenterApiConfig.token | cloud-handoff

## Decision Defaults
Priority | Lane | Owner | Title | CurrentValueStatus | RecommendedValue | DashboardPage | DashboardField | UserAction | CodexCanContinue | NoGoRule
P0 | Business Legal | User | Business name candidate | Saved matches recommendation | Porter Labs LLC | pages/collaboration.html | decisions.businessName | Confirm the final legal/business name, save it in the dashboard, and upload sanitized filing evidence when available. | Keep product copy using NyrA Swarm Little Buddy Pro and leave live Stripe identity blocked until the saved legal name is real. | A saved business name does not clear attorney/accountant review, entity evidence, tax review, or live Stripe authorization.
P0 | Business Legal | User | Entity path | Saved matches recommendation | SC LLC | pages/collaboration.html | decisions.entityPath | Choose SC LLC or another documented entity path, then save the decision and upload the filing or accountant/legal note. | Keep legal docs and Stripe setup packets ready without marking entity status complete. | Paid public launch remains blocked until the entity/contact path is chosen and reviewed.
P0 | Business Legal | User | Tax collection/accounting path | Saved matches recommendation | Stripe Tax now | pages/collaboration.html | decisions.taxDecision | Choose Stripe Tax now, accountant first, or SC-only beta in the dashboard. Get accountant/legal review before live public charging. | Keep Stripe Tax and billing docs wired as the default path, but keep live mode blocked until review is recorded. | This is not tax advice and does not replace accountant/legal approval.
P0 | Payments Licensing | User | Monthly subscription price | Saved matches recommendation | $25.00 | pages/pricing.html | decisions.monthlyPriceCents | Save the approved monthly price in cents before creating the Stripe Price. | Use 2500 cents in dry-run Stripe commands and launch copy drafts until you approve or override the price. | Do not create a live Stripe Price until the approved price is saved.
P0 | Payments Licensing | User | Hosted AI cap | Saved matches recommendation | 300 hosted AI messages/month until measured usage proves more headroom | pages/pricing.html | decisions.hostedAiCap | Save the customer-facing hosted AI cap and over-cap behavior before checkout copy is published. | Keep marketing and policy copy aligned to a capped hosted-AI beta with BYOK planned later. | Do not publish unlimited hosted-AI claims or live checkout copy without this cap.
P0 | Support Ops | User | Support inbox | Saved matches recommendation | support@support.porterlabz.com | pages/support.html | decisions.supportEmail | Confirm you own the inbox, send a test ticket, reply, then mark billingRehearsal.supportInboxConfirmed as Yes. | Keep support macros, diagnostics, and policy contact fields pointed at the saved support address. | Support email text alone does not clear the support roundtrip blocker.
P0 | Business Legal | User | Refund and cancellation policy | Suggested - not saved | All purchases final, with legal/billing-error exceptions | pages/refund-cancellation.html | policy.review.refundCancellation | Have the refund/cancellation language reviewed before paid launch and upload legal review evidence. | Keep policy drafts and Stripe support text aligned to this rule until legal review changes it. | A drafted policy is not legal approval.
P0 | Payments Licensing | User + Codex | Billing entitlement storage host | Saved matches recommendation | Cloudflare Worker + D1 | pages/billing-rehearsal.html | billingDeployment.storageHostDecision | Approve Cloudflare billing storage and paste the D1 database ID after creation. | Continue building and testing the billing Worker/D1 path locally without storing customer state on this computer. | Do not enable hosted checkout until D1 and billing Worker deployment are verified.
P0 | Cloud Platform | User + Codex | Cloud command-center stack | Saved different value | Cloudflare Pages + Workers + D1 + R2 | pages/cloud.html | cloudMigration.target | Approve the Cloudflare account/domain/admin/access handoff so the dashboard can move off local files. | Keep Pages/Worker/D1/R2 deploy packs and cloud sync tests current until credentials and IDs are supplied. | Local dashboard files remain the source of truth until a protected cloud deployment and sync roundtrip pass.
P0 | Cloud Platform | User + Codex | Cloud access model | Saved matches recommendation | Cloudflare Access + private bearer token | pages/cloud.html | cloudMigration.accessDecision | Choose Cloudflare Access plus private token, then save the access model and admin email. | Keep no-secret browser localStorage token handling and Worker auth checks in place. | Do not publish a dashboard with business records without private access protection.
P0 | Release Ops | User | Release channel | Saved matches recommendation | Direct download beta + Microsoft Store prep | pages/collaboration.html | decisions.releaseChannel | Choose direct download beta, Microsoft Store, or both before release rehearsal. | Keep direct-download release notes, rollback, installer rehearsal, and signed-installer evidence ready. | Unsigned direct download remains internal-alpha only until trust/signing evidence clears.
P0 | Release Ops | User | Code-signing path | Saved matches recommendation | Microsoft Trusted Signing first | pages/collaboration.html | decisions.codeSigningDecision | Choose Microsoft Trusted Signing, Microsoft Store first, OV certificate, or hold. Upload signing/store evidence before paid beta. | Keep release trust pack and installer rehearsal wired to Trusted Signing, signed-installer, or store-trusted evidence. | Do not distribute a paid public installer without a signed or store-trusted path.
P1 | Release/Product | Codex | App version path | Saved different value | Desktop paid beta first; mobile companion after desktop money path is proven | pages/app-version.html | appVersion.mobileCompanionBoundary | Use the App Version page to record any required mobile companion boundaries or app-store goals. | Continue mapping Capacitor/mobile companion scope while keeping desktop beta as the launch target. | Do not delay desktop paid beta for mobile unless the user explicitly changes launch priority.
P1 | Marketing Visuals | Codex | Shipping visuals | Suggested - not saved | No until final app, billing, support, and consent flows are frozen | pages/visuals.html | visualProduction.finalScreenshotsApproved | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | Keep screenshot checklist, diagrams, marketing kit, and demo shot list refreshed from the current product state. | Do not publish launch ads or checkout visuals until final screenshots are approved.

## Payment Launch Pack
Phase | Priority | Owner | Status | Label | Action | EvidenceNeeded | DashboardPage | DashboardField | UploadSlot | VerificationCommand | NoGoRule
1. Legal And Stripe Identity | P0 | User | Waiting on user | Attorney/accountant review approved for paid beta | Mark attorney/accountant review approved only after paid-beta policies, tax, refund, privacy, and support language are cleared. | Save billingRehearsal.attorneyReviewStatus and upload evidence to legal-review when available. | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | legal-review | npm run test:policy-readiness && npm run billing:live-preflight -- --mode test --allow-blocked | Do not mark this ready until the saved dashboard state or uploaded evidence proves it.
8. Live Payment Gate | P0 | User + Codex | User + Codex gated | Billing rehearsal mode set to live for final money preflight | Keep rehearsal mode in test until test checkout, portal, webhook, support, legal, domain, secrets, and release gates pass. | Save billingRehearsal.mode and upload evidence to stripe-screenshots when available. | pages/billing-rehearsal.html | billingRehearsal.mode | stripe-screenshots | npm run billing:live-preflight -- --mode live | Do not mark this ready until the saved dashboard state or uploaded evidence proves it.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | STRIPE_SECRET_KEY | Cloudflare billing Worker secret and temporary billing rehearsal shell; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: STRIPE_SECRET_KEY | cloud-handoff | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | STRIPE_WEBHOOK_SECRET | Cloudflare billing Worker secret and temporary billing rehearsal shell; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: STRIPE_WEBHOOK_SECRET | cloud-handoff | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
3. Stripe Product And Price | P0 | User | Secret-store only | NYRA_STRIPE_PRICE_PRO_MONTHLY | Cloudflare billing Worker secret and temporary billing rehearsal shell; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: NYRA_STRIPE_PRICE_PRO_MONTHLY | cloud-handoff | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
6. Support And Domain | P0 | User | Secret-store only | NYRA_BILLING_SUCCESS_URL | Cloudflare billing Worker secret or hosted backend environment variable; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_SUCCESS_URL | cloud-handoff | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
6. Support And Domain | P0 | User | Secret-store only | NYRA_BILLING_CANCEL_URL | Cloudflare billing Worker secret or hosted backend environment variable; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_CANCEL_URL | cloud-handoff | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
6. Support And Domain | P0 | User | Secret-store only | NYRA_BILLING_RETURN_URL | Cloudflare billing Worker secret or hosted backend environment variable; verify with npm run billing:live-preflight -- --mode test --allow-blocked. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_RETURN_URL | cloud-handoff | npm run billing:live-preflight -- --mode test --allow-blocked | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_LICENSE_API_TOKEN | Cloudflare billing Worker secret and desktop activation configuration; verify with npm run cloud:billing:check && npm run test:cloud-billing-worker. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_API_TOKEN | cloud-handoff | npm run cloud:billing:check && npm run test:cloud-billing-worker | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_LICENSE_SIGNING_SECRET | Cloudflare billing Worker and mobile bridge Worker secret; verify with npm run cloud:billing:check && npm run test:cloud-billing-worker && npm run cloud:mobile-bridge:check. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_SIGNING_SECRET | cloud-handoff | npm run cloud:billing:check && npm run test:cloud-billing-worker && npm run cloud:mobile-bridge:check | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_MOBILE_BRIDGE_TOKEN | Cloudflare mobile bridge Worker secret and temporary bridge test shell; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_MOBILE_BRIDGE_TOKEN | cloud-handoff | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_OPENAI_API_KEY | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_OPENAI_API_KEY | cloud-handoff | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_ANTHROPIC_API_KEY | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_ANTHROPIC_API_KEY | cloud-handoff | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_GEMINI_API_KEY | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_GEMINI_API_KEY | cloud-handoff | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_GROK_API_KEY | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_GROK_API_KEY | cloud-handoff | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.
7. Secret Store And Rehearsal | P0 | User | Secret-store only | NYRA_ANDROID_DOWNLOAD_TICKET_SECRET | Cloudflare mobile bridge Worker secret; verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | Set via Wrangler secret, deployment secret manager, or temporary shell only. Generated docs may show placeholders only. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_ANDROID_DOWNLOAD_TICKET_SECRET | cloud-handoff | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Never paste raw secret values into dashboard fields, Markdown files, CSV files, screenshots, source code, repo state, or chat.

## Support Ops Pack
Id | Phase | Priority | Owner | Status | Label | Action | EvidenceNeeded | DashboardPage | DashboardField | UploadSlot | VerificationCommand | NoGoRule
support-email-saved | 1. Public Support Identity | P0 | User | Ready | Support email saved | Save the support address customers will see in the app, Stripe receipts, public policies, and launch site. | Save decisions.supportEmail in the dashboard and upload sanitized support evidence to domain-email. | pages/support.html | decisions.supportEmail | domain-email | npm run support:ops-pack && npm run test:support-ops-pack | No paid checkout without a public support contact.
support-inbox-roundtrip | 1. Public Support Identity | P0 | User | Ready | Support inbox ticket roundtrip confirmed | Send a test customer email to the support inbox, reply from the inbox, and upload sanitized proof of the roundtrip. | Save billingRehearsal.supportInboxConfirmed in the dashboard and upload sanitized support evidence to support-roundtrip. | pages/support.html | billingRehearsal.supportInboxConfirmed | support-roundtrip | npm run support:ops-pack && npm run test:support-ops-pack | No paid beta until a real support inbox can receive and answer a customer ticket.
public-domain-support-path | 2. Public Policy And Domain | P0 | User | Ready | Public domain and policy support path saved | Save the public product domain so privacy, terms, refund, cancellation, support, checkout success, and portal return URLs can match. | Save decisions.domain in the dashboard and upload sanitized support evidence to domain-email. | pages/support.html | decisions.domain | domain-email | npm run public:launch-config && npm run test:public-launch-config | No public checkout unless policy/support URLs are on the intended public domain.
diagnostics-export | 3. Customer Diagnostics | P0 | Codex | Ready | Redacted support diagnostics export exists | Keep Settings diagnostics export available and redacted before every release candidate. | Save supportOps.diagnosticsStatus in the dashboard and upload sanitized support evidence to qa-evidence. | pages/support.html | supportOps.diagnosticsStatus | qa-evidence | npm run test:support-readiness && npm run test:support-diagnostics-runtime | Support must not ask customers for raw chats, API keys, tokens, full card numbers, screenshots with secrets, or private files.
support-runbook | 4. Support Process | P0 | Codex | Ready | Support runbook and inbox setup docs exist | Keep support categories, evidence rules, response targets, canned replies, and inbox setup docs current with the shipping product. | Save supportOps.runbookStatus in the dashboard and upload sanitized support evidence to qa-evidence. | pages/support.html | supportOps.runbookStatus | qa-evidence | npm run test:support-readiness | No paid beta without a written support process for install, activation, billing, cancellation, privacy, and computer-control tickets.
billing-cancellation-support | 5. Billing Support | P0 | User + Codex | Ready | Customer Portal cancellation and invoice support configured | Configure Stripe Customer Portal for cancellation, invoice history, and payment method updates; then test the support reply path. | Save billingRehearsal.customerPortalConfigured in the dashboard and upload sanitized support evidence to stripe-screenshots. | pages/support.html | billingRehearsal.customerPortalConfigured | stripe-screenshots | npm run payment:launch-pack && npm run test:payment-launch-pack | Do not take recurring subscription money without a customer cancellation path.
hosted-billing-support-links | 5. Billing Support | P0 | User + Codex | Ready | Hosted billing support links saved | Save hosted billing backend and Stripe webhook URLs so support can distinguish checkout, portal, webhook, and activation failures. | Save billingRehearsal.backendBaseUrl in the dashboard and upload sanitized support evidence to cloud-handoff. | pages/support.html | billingRehearsal.backendBaseUrl | cloud-handoff | npm run billing:live-preflight -- --mode test --allow-blocked | Support cannot debug real customer billing until hosted backend and webhook URLs are known.
legal-support-review | 6. Legal And Policy Review | P0 | User | Waiting on handoff | Support, refund, privacy, and cancellation language reviewed | Review final-sale, cancellation, support, privacy, and paid-beta language with an attorney/accountant or explicitly mark approved after review. | Save billingRehearsal.attorneyReviewStatus in the dashboard and upload sanitized support evidence to legal-review. | pages/support.html | billingRehearsal.attorneyReviewStatus | legal-review | npm run test:policy-readiness | Do not launch paid beta while support/refund/cancellation language is unreviewed.
support-visuals-current | 7. Support Visual Evidence | P0 | Codex | Waiting on product freeze | Support screenshots match shipping app | Refresh support, diagnostics, billing, cancellation, and activation screenshots after the shipping UI and support paths are frozen. | Save visualProduction.finalScreenshotsApproved in the dashboard and upload sanitized support evidence to product-screenshots. | pages/support.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:pack && npm run test:visual-production-pack | Do not use support visuals that show stale UI, wrong support email, wrong policy URLs, or incomplete billing flow.

## Release Trust Pack
Phase | Priority | Owner | Status | Label | Action | EvidenceNeeded | DashboardPage | DashboardField | UploadSlot | VerificationCommand | NoGoRule
4. Signed Or Store Evidence | P0 | User + Codex | User + Codex gated | Paid beta installer is signed or store-trusted | Produce signed direct-download installer evidence or store-trusted package/listing evidence before any paid beta customer receives the build. | Save releasePackage.signingStatus and upload sanitized signature/store evidence to code-signing. Never upload private keys, PFX passwords, token PINs, or Partner Center secrets. | pages/release-package.html | releasePackage.signingStatus | code-signing | npm run release:installer:rehearsal && npm run release:evidence && npm run release:candidate:preflight | No paid beta customer receives an unsigned direct-download installer or raw win-unpacked folder.
2. Signing Build Readiness | P0 | User + Codex | blocked | Windows signing readiness is proven | Finish Microsoft Artifact Signing or PFX handoffs so Codex can produce a signed Windows installer without storing secrets in the repo. | Windows signing readiness is Microsoft Artifact Signing Handoffs Missing. Run npm run release:windows-signing:preflight, then finish the listed Microsoft Artifact Signing or PFX handoffs before building a paid beta installer. | pages/release-package.html | windowsSigningReadiness.status | code-signing | npm run release:windows-signing:preflight && npm run test:windows-signing-readiness | Paid beta remains blocked until the release-candidate preflight shows the installer trust gate as pass.
4. Signed Or Store Evidence | P0 | User + Codex | blocked | Trusted installer evidence clears release candidate | Choose the release trust path and produce signed or store-trusted installer evidence before paid beta. | Choose the release trust path and produce signed or store-trusted installer evidence before paid beta. | pages/release-package.html | releasePackage.signingStatus | code-signing | npm run release:windows-signing:preflight && npm run release:trust:pack && npm run release:candidate:preflight | Paid beta remains blocked until the release-candidate preflight shows the installer trust gate as pass.

## Version Control Pack
Phase | Priority | Owner | Status | Label | Action | EvidenceNeeded | DashboardPage | DashboardField | UploadSlot | VerificationCommand | NoGoRule
2. Repository Baseline | P0 | User | Waiting on handoff | GitHub remote or repo URL saved | Save the intended GitHub repository owner/name or remote URL in the dashboard. | Save versionControl.repoRemoteUrl in the dashboard and upload sanitized repo/CI evidence to version-control. | pages/version-control.html | versionControl.repoRemoteUrl | version-control | npm run version:control-pack && npm run test:version-control-pack | No public paid release until the source repo and release evidence location are known.
2. Repository Baseline | P0 | User + Codex | Waiting on handoff | GitHub repo creation or push path available | Authenticate GitHub CLI or save an existing remote URL in the dashboard. | Save versionControl.repoRemoteUrl in the dashboard and upload sanitized repo/CI evidence to version-control. | pages/version-control.html | versionControl.repoRemoteUrl | version-control | npm run version:control-pack && npm run test:version-control-pack | No paid beta release until source history can be pushed to the chosen GitHub repository.
2. Repository Baseline | P0 | User + Codex | Waiting on handoff | Push dry-run readiness captured | Save or configure the intended GitHub origin remote, then rerun the dry-run push check before any tag or signing handoff. | Save versionControl.repoRemoteUrl in the dashboard and upload sanitized repo/CI evidence to version-control. | pages/version-control.html | versionControl.repoRemoteUrl | version-control | npm run version:control-pack && npm run test:version-control-pack | No release tag or signed package handoff is complete until a non-mutating push dry-run has been captured for the chosen remote.

## Visual Production Pack
Phase | Priority | Owner | Status | Label | Action | EvidenceNeeded | DashboardPage | DashboardField | UploadSlot | VerificationCommand | NoGoRule
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Desktop Alpha83 answer-first response | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/launch_command_center/visuals/alpha83_desktop_answer_first.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Idle NyrA buddy | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/nyra-compact-character-smoke.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Right-click command menu | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/nyra-action-router-smoke.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Live voice controls | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/computer-use-realtime.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Wake-gated pause/listening behavior | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/nyra-buddy-speaker.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Single buddy with right-click chat panel | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/launch_command_center/visuals/alpha66_single_buddy_panel_smoke_settled.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Screen-look permission state | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/computer-use-screen-look.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Camera permission state | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/computer-use-camera.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Computer-control active state | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/computer-use-control.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Stop button / interruption evidence | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/computer-use-interrupt.png; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Android floating buddy over launcher | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. Current evidence is 0.1.0-alpha.80; shipping app is 0.1.0-alpha.83. | Refresh or approve docs/launch_command_center/visuals/alpha80_emulator_after_show_bot.png; current status is Captured - refresh before beta - stale evidence. Version mismatch: evidence=0.1.0-alpha.80, current=0.1.0-alpha.83. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Android foreground panel and answer-first swarm state | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. Current evidence is 0.1.0-alpha.80; shipping app is 0.1.0-alpha.83. | Refresh or approve docs/launch_command_center/visuals/alpha80_emulator_panel.png; current status is Captured - refresh before beta - stale evidence. Version mismatch: evidence=0.1.0-alpha.80, current=0.1.0-alpha.83. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
5. Other Visual Evidence | P0 | Codex | Blocked | Android alpha83 responsive Command surface | Refresh after each mobile Command surface or autonomous-run layout change. | Upload sanitized evidence to product-screenshots when this asset exists. | pages/visuals.html | visualProduction.notes | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Android alpha83 Hide Bot recovery surface | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. Current evidence is 0.1.0-alpha.80; shipping app is 0.1.0-alpha.83. | Refresh or approve docs/launch_command_center/visuals/alpha80_emulator_hidden_recovery.png; current status is Captured - refresh before beta - stale evidence. Version mismatch: evidence=0.1.0-alpha.80, current=0.1.0-alpha.83. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
2. Replace Diagram With App Screen | P1 | User + Codex | Partial | Billing activation screen | Replace the diagram-only evidence with a current app screenshot after the relevant billing/support flow exists. | Refresh or approve docs/launch_command_center/visuals/08_license_activation_flow.jpg; current status is Partial. | pages/visuals.html | visualProduction.notes | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
3. Billing Portal Capture | P0 | User + Codex | Blocked | Customer Portal screen | After Stripe Customer Portal is configured, capture the real customer portal screen and attach sanitized evidence to the dashboard. | Upload sanitized evidence to stripe-screenshots when this asset exists. | pages/visuals.html | billingRehearsal.customerPortalConfigured | stripe-screenshots | npm run billing:live-preflight -- --mode test --allow-blocked && npm run visuals:pack | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
1. Refresh Shipping Screenshot | P1 | Codex | Refresh required | Command center Collaboration page | Refresh this screenshot from the current shipping build after UI, consent, billing, support, and release messaging are frozen. | Refresh or approve docs/launch_command_center/visuals/07_command_center_collaboration_page.jpg; current status is Captured - refresh before beta. | pages/visuals.html | visualProduction.finalScreenshotsApproved | product-screenshots | npm run visuals:inventory && npm run test:visual-assets | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
2. Replace Diagram With App Screen | P1 | User + Codex | Partial | License activation flow | Replace the diagram-only evidence with a current app screenshot after the relevant billing/support flow exists. | Refresh or approve docs/launch_command_center/visuals/08_license_activation_flow.jpg; current status is Partial. | pages/visuals.html | visualProduction.notes | marketing-assets | npm run visuals:inventory && npm run visuals:pack | Do not mark paid-beta visuals approved until the asset matches the exact shipping app and current public offer.
4. Demo And Ad Video | P1 | Codex | Planned | 90-second product demo | Record this video only after final UI, pricing, hosted AI cap, support path, policy URLs, checkout URL, and screenshots match the shipping build. | Refresh or approve docs/launch_command_center/marketing/video-shotlist.csv; current status is Planned. | pages/visuals.html | visualProduction.demoVideoStatus | marketing-assets | npm run marketing:kit && npm run visuals:pack | Do not publish demo or ad video with placeholder pricing, stale UI, disabled checkout confusion, or unapproved claims.
4. Demo And Ad Video | P1 | Codex | Planned | 30-second founding beta ad | Record this video only after final UI, pricing, hosted AI cap, support path, policy URLs, checkout URL, and screenshots match the shipping build. | Refresh or approve docs/launch_command_center/marketing/video-shotlist.csv; current status is Planned. | pages/visuals.html | visualProduction.demoVideoStatus | marketing-assets | npm run marketing:kit && npm run visuals:pack | Do not publish demo or ad video with placeholder pricing, stale UI, disabled checkout confusion, or unapproved claims.

## Cloud Deploy Pack
Phase | Priority | Owner | Status | Label | Action | EvidenceNeeded | DashboardPage | DashboardField | UploadSlot | VerificationCommand | NoGoRule
5. First Cloud Sync | P1 | Codex | post-deploy | Cloud API URL available for sync | After Worker deployment, set NYRA_COMMAND_CENTER_API_URL in a temporary shell and the browser Cloud Connection URL field. | Temporary shell value or browser Cloud Connection config only. The API URL can be saved; private tokens cannot. | pages/cloud.html | cloudSync.apiUrl | cloud-handoff | npm run cloud:command-center:deploy:preflight | Do not treat cloud as source of truth until this action is proven by dashboard state, config, command output, or cloud health check.
5. First Cloud Sync | P1 | Codex | post-deploy | Cloud API token available for sync | Set NYRA_COMMAND_CENTER_TOKEN in a temporary shell using the same private value as NYRA_COMMAND_TOKEN after the Worker secret is created. | Use only temporary shell or browser localStorage. Never paste the bearer token into dashboard state, CSV, Markdown, screenshots, repo files, or chat. | pages/cloud.html | browser localStorage only: nyraCommandCenterApiConfig.token | cloud-handoff | npm run cloud:command-center:deploy:preflight | Do not treat cloud as source of truth until this action is proven by dashboard state, config, command output, or cloud health check.

## Cloudflare Discovery
Phase | Priority | Owner | Status | Label | Action | Command | DashboardPage | DashboardField | NoGoRule
4. Host Dashboard | P0 | User + Codex | Waiting on Pages custom domain | Map and protect command-center domain | Add command.porterlabz.com as a custom domain on the nyra-command-center-dashboard Pages project, verify DNS/SSL, and apply the selected private access policy before publishing current business records. | npx wrangler pages project list --json | pages/cloud.html | cloudMigration.dashboardDomain | Do not describe the private command center as hosted at the custom domain until Wrangler discovery lists that exact domain and access protection is verified.
4. Verify | P1 | Codex | Open | Refresh Cloudflare discovery | Rerun discovery after any Cloudflare dashboard or Wrangler resource change so the command center stays current. | npm run cloudflare:discover | pages/cloudflare-discovery.html | cloudMigration.notes | Cloudflare API tokens, Worker bearer tokens, recovery codes, Stripe secrets, private keys, and password material must stay in Wrangler secrets, Cloudflare dashboard secret stores, browser localStorage, or a temporary shell only. This discovery pack stores non-secret resource names/IDs and redacted account context only.

## Cloud Bootstrap
Phase | Priority | Owner | Status | Label | Action | Command | DashboardPage | DashboardField | VerificationCommand | NoGoRule
1. Authentication | P0 | User | Ready | Cloudflare API token required | Create a scoped Cloudflare API token for the account that will host NyrA, set it as CLOUDFLARE_API_TOKEN in the local shell or automation secret store, then rerun npm run cloudflare:discover. | npm run cloudflare:discover | pages/cloud-bootstrap.html | cloudMigration.accountReady | npm run cloudflare:discover | Never store Cloudflare tokens, API keys, recovery codes, or password material in repo files or dashboard state.
1. Authentication | P1 | User | Ready | Wrangler login | If you are sitting at the Windows desktop and prefer browser auth, run npx wrangler login and approve the Cloudflare account that will host NyrA. Automation still needs CLOUDFLARE_API_TOKEN. | npx wrangler login | pages/cloud-bootstrap.html | cloudMigration.accountReady | npm run cloudflare:discover | Never store Cloudflare tokens, API keys, recovery codes, or password material in repo files or dashboard state.
2. Remote Resources | P0 | User + Codex | Ready for config review | D1: nyra_command_center | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npx wrangler d1 create nyra_command_center | pages/cloud.html | cloudMigration.d1DatabaseId | npm run cloudflare:discover | Do not deploy command-center Worker production until this D1 database_id is concrete in wrangler.jsonc.
2. Remote Resources | P0 | User + Codex | Ready for config review | D1: nyra_billing | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npx wrangler d1 create nyra_billing | pages/cloud-billing.html | billingCloud.d1DatabaseId | npm run cloudflare:discover | Do not deploy billing Worker production until this D1 database_id is concrete in wrangler.jsonc.
2. Remote Resources | P0 | User + Codex | Ready for config review | R2: nyra-command-center-uploads | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npx wrangler r2 bucket create nyra-command-center-uploads | pages/cloud.html | cloudMigration.r2Bucket | npm run cloudflare:discover | Keep the handoff upload bucket private; never enable public bucket access for private launch evidence.
2. Remote Resources | P0 | User + Codex | Ready for config review | R2: nyra-mobile-support-logs | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npx wrangler r2 bucket create nyra-mobile-support-logs | pages/cloud-mobile-bridge.html | mobileBridge.r2BucketName | npm run cloudflare:discover && npm run cloud:mobile-bridge:check | Keep mobile support diagnostics private; only redacted support-log readbacks may be exposed to support flows.
2. Remote Resources | P1 | User + Codex | Ready for config review | R2: nyra-android-releases | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npx wrangler r2 bucket create nyra-android-releases | pages/cloud-mobile-bridge.html | mobileBridge.androidReleasesBucketName | npm run cloudflare:discover && npm run cloud:mobile-bridge:check | Serve APK downloads through ticketed Worker routes, not public unauthenticated bucket URLs.
2. Remote Resources | P1 | User + Codex | Ready for config review | Pages: nyra-command-center-dashboard | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npx wrangler pages project create nyra-command-center-dashboard --production-branch main | pages/cloud.html | cloudPages.projectName | npm run cloudflare:discover | Protect the dashboard with Cloudflare Access or equivalent private access before storing real business records.
2. Remote Resources | P1 | Codex | Ready for deploy review | Worker: nyra-command-center-api | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npm run cloud:command-center:deploy | pages/cloud.html | cloudSync.apiUrl | npm run cloud:command-center:health | Do not deploy until command-center D1/R2, ALLOWED_ORIGIN, and NYRA_COMMAND_TOKEN are configured.
2. Remote Resources | P1 | Codex | Ready for deploy review | Worker: nyra-billing-api | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npm run cloud:billing:deploy | pages/cloud-billing.html | billingCloud.workerUrl | npm run cloud:billing:check | Do not deploy live billing until Stripe test-mode rehearsal, secrets, Customer Portal, support, and policy gates pass.
2. Remote Resources | P1 | Codex | Ready for deploy review | Worker: nyra-mobile-bridge-api | Run discovery/config sync and verify the non-secret ID or URL is saved in the dashboard before deployment. | npm run cloud:mobile-bridge:bootstrap -- --worker-url=https://bridge.porterlabz.com --write-state | pages/cloud-mobile-bridge.html | mobileBridge.workerUrl | npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security | Do not rebuild Android paid-beta against this Worker until R2 APK hosting, provider secrets, device-token auth, and phone self-test evidence pass.
3. Config Sync | P0 | Codex | Waiting on prior gates | sync non secret config | Apply saved non-secret dashboard values to production Worker configs and verify the mobile bridge bootstrap plan. | npm run cloud:command-center:config:sync && npm run cloud:billing:config:sync && npm run cloud:mobile-bridge:bootstrap -- --dry-run --skip-secrets --skip-deploy | pages/cloud-bootstrap.html |  | npm run cloud:command-center:config:sync && npm run cloud:billing:config:sync && npm run cloud:mobile-bridge:bootstrap -- --dry-run --skip-secrets --skip-deploy | This must not write Stripe secrets, bearer tokens, or Cloudflare tokens into repo files.
4. Secrets | P0 | User + Codex | Waiting on prior gates | command token secret | Set the private command-center API bearer token through Wrangler secrets only. | npx wrangler secret put NYRA_COMMAND_TOKEN --cwd cloud/command-center-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_COMMAND_TOKEN --cwd cloud/command-center-worker --env production | Do not paste this token into dashboard fields, repo files, Markdown, CSV, screenshots, or chat.
4. Secrets | P0 | User + Codex | Waiting on prior gates | billing secret stripe secret key | Set STRIPE_SECRET_KEY for the billing Worker through Wrangler secrets only. | npx wrangler secret put STRIPE_SECRET_KEY --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put STRIPE_SECRET_KEY --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P0 | User + Codex | Waiting on prior gates | billing secret stripe webhook secret | Set STRIPE_WEBHOOK_SECRET for the billing Worker through Wrangler secrets only. | npx wrangler secret put STRIPE_WEBHOOK_SECRET --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put STRIPE_WEBHOOK_SECRET --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P0 | User + Codex | Waiting on prior gates | billing secret nyra stripe price pro monthly | Set NYRA_STRIPE_PRICE_PRO_MONTHLY for the billing Worker through Wrangler secrets only. | npx wrangler secret put NYRA_STRIPE_PRICE_PRO_MONTHLY --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_STRIPE_PRICE_PRO_MONTHLY --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P0 | User + Codex | Waiting on prior gates | billing secret nyra billing success url | Set NYRA_BILLING_SUCCESS_URL for the billing Worker through Wrangler secrets only. | npx wrangler secret put NYRA_BILLING_SUCCESS_URL --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_BILLING_SUCCESS_URL --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | billing secret nyra billing cancel url | Set NYRA_BILLING_CANCEL_URL for the billing Worker through Wrangler secrets only. | npx wrangler secret put NYRA_BILLING_CANCEL_URL --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_BILLING_CANCEL_URL --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | billing secret nyra billing return url | Set NYRA_BILLING_RETURN_URL for the billing Worker through Wrangler secrets only. | npx wrangler secret put NYRA_BILLING_RETURN_URL --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_BILLING_RETURN_URL --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | billing secret nyra license api token | Set NYRA_LICENSE_API_TOKEN for the billing Worker through Wrangler secrets only. | npx wrangler secret put NYRA_LICENSE_API_TOKEN --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_LICENSE_API_TOKEN --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | billing secret nyra license signing secret | Set NYRA_LICENSE_SIGNING_SECRET for the billing Worker through Wrangler secrets only. | npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/billing-worker --env production | Do not paste Stripe, license, or webhook secret values into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | mobile bridge secret nyra mobile bridge token | Set NYRA_MOBILE_BRIDGE_TOKEN for the mobile bridge Worker through Wrangler secrets only. | npx wrangler secret put NYRA_MOBILE_BRIDGE_TOKEN --cwd cloud/mobile-bridge-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_MOBILE_BRIDGE_TOKEN --cwd cloud/mobile-bridge-worker --env production | Do not paste bridge tokens, provider API keys, license signing secrets, or Android ticket secrets into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | mobile bridge secret nyra openai api key | Set NYRA_OPENAI_API_KEY for the mobile bridge Worker through Wrangler secrets only. | npx wrangler secret put NYRA_OPENAI_API_KEY --cwd cloud/mobile-bridge-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_OPENAI_API_KEY --cwd cloud/mobile-bridge-worker --env production | Do not paste bridge tokens, provider API keys, license signing secrets, or Android ticket secrets into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | mobile bridge secret nyra anthropic api key | Set NYRA_ANTHROPIC_API_KEY for the mobile bridge Worker through Wrangler secrets only. | npx wrangler secret put NYRA_ANTHROPIC_API_KEY --cwd cloud/mobile-bridge-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_ANTHROPIC_API_KEY --cwd cloud/mobile-bridge-worker --env production | Do not paste bridge tokens, provider API keys, license signing secrets, or Android ticket secrets into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | mobile bridge secret nyra gemini api key | Set NYRA_GEMINI_API_KEY for the mobile bridge Worker through Wrangler secrets only. | npx wrangler secret put NYRA_GEMINI_API_KEY --cwd cloud/mobile-bridge-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_GEMINI_API_KEY --cwd cloud/mobile-bridge-worker --env production | Do not paste bridge tokens, provider API keys, license signing secrets, or Android ticket secrets into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | mobile bridge secret nyra grok api key | Set NYRA_GROK_API_KEY for the mobile bridge Worker through Wrangler secrets only. | npx wrangler secret put NYRA_GROK_API_KEY --cwd cloud/mobile-bridge-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_GROK_API_KEY --cwd cloud/mobile-bridge-worker --env production | Do not paste bridge tokens, provider API keys, license signing secrets, or Android ticket secrets into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | mobile bridge secret nyra license signing secret | Set NYRA_LICENSE_SIGNING_SECRET for the mobile bridge Worker through Wrangler secrets only. | npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/mobile-bridge-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/mobile-bridge-worker --env production | Do not paste bridge tokens, provider API keys, license signing secrets, or Android ticket secrets into the dashboard or repo.
4. Secrets | P1 | User + Codex | Waiting on prior gates | mobile bridge secret nyra android download ticket secret | Set NYRA_ANDROID_DOWNLOAD_TICKET_SECRET for the mobile bridge Worker through Wrangler secrets only. | npx wrangler secret put NYRA_ANDROID_DOWNLOAD_TICKET_SECRET --cwd cloud/mobile-bridge-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler secret put NYRA_ANDROID_DOWNLOAD_TICKET_SECRET --cwd cloud/mobile-bridge-worker --env production | Do not paste bridge tokens, provider API keys, license signing secrets, or Android ticket secrets into the dashboard or repo.
5. Migrations | P1 | User + Codex | Waiting on prior gates | command center migrations | Apply command-center D1 schema after the concrete database ID is configured. | npx wrangler d1 migrations apply nyra_command_center --cwd cloud/command-center-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler d1 migrations apply nyra_command_center --cwd cloud/command-center-worker --env production | Do not apply migrations to the wrong Cloudflare account or placeholder database ID.
5. Migrations | P1 | User + Codex | Waiting on prior gates | billing migrations | Apply billing D1 schema after the concrete database ID is configured. | npx wrangler d1 migrations apply nyra_billing --cwd cloud/billing-worker --env production | pages/cloud-bootstrap.html |  | npx wrangler d1 migrations apply nyra_billing --cwd cloud/billing-worker --env production | Do not run live billing until Stripe test-mode and legal/support gates pass.
6. Deploy | P1 | Codex | Waiting on prior gates | deploy command center worker | Deploy the private command-center Worker API. | npm run cloud:command-center:deploy | pages/cloud-bootstrap.html |  | npm run cloud:command-center:deploy | Do not deploy with placeholder D1 ID or placeholder ALLOWED_ORIGIN.
6. Deploy | P1 | Codex | Waiting on prior gates | deploy command center pages | Deploy the command-center dashboard artifact to Cloudflare Pages. | npm run cloud:command-center:pages:deploy | pages/cloud-bootstrap.html |  | npm run cloud:command-center:pages:deploy | Protect dashboard access before storing real business records or user files.
6. Deploy | P1 | Codex | Waiting on prior gates | deploy billing worker | Deploy the billing Worker after test-mode payment rehearsal inputs are complete. | npm run cloud:billing:deploy | pages/cloud-bootstrap.html |  | npm run cloud:billing:deploy | Do not expose live checkout while deployability preflight still reports P0 live-money blockers.
6. Deploy | P1 | Codex | Waiting on prior gates | deploy mobile bridge worker | Create/verify mobile bridge R2 buckets, upload the APK, deploy the Worker, and prove status/update/APK ticket/support-log/chat before saving state. | npm run cloud:mobile-bridge:bootstrap -- --worker-url=https://bridge.porterlabz.com --write-state | pages/cloud-bootstrap.html |  | npm run cloud:mobile-bridge:bootstrap -- --worker-url=https://bridge.porterlabz.com --write-state | Do not replace the Android bundled bridge URL for paid beta until this post-deploy smoke passes and the shared alpha token is removed.
7. First Sync | P1 | Codex | Waiting on prior gates | first cloud roundtrip | Prove cloud command-center state can be pushed, scanned, safely ingested, and read back. | npm run cloud:command-center:health && npm run cloud:command-center:push && npm run cloud:command-center:scan && npm run cloud:command-center:ingest && npm run cloud:command-center:roundtrip | pages/cloud-bootstrap.html |  | npm run cloud:command-center:health && npm run cloud:command-center:push && npm run cloud:command-center:scan && npm run cloud:command-center:ingest && npm run cloud:command-center:roundtrip | Use only temporary shell env vars for NYRA_COMMAND_CENTER_API_URL and NYRA_COMMAND_CENTER_TOKEN.
7. First Sync | P1 | Codex | Waiting on prior gates | billing live preflight test mode | Run a guarded test-mode billing go-live rehearsal after cloud URLs and secrets exist. | npm run billing:live-preflight -- --mode test --allow-blocked | pages/cloud-bootstrap.html |  | npm run billing:live-preflight -- --mode test --allow-blocked | Do not run live-mode billing rehearsal until user explicitly confirms live Stripe readiness.
7. First Sync | P1 | User + Codex | Waiting on prior gates | mobile phone self test after deploy | Ingest and verify a physical-phone self-test after the deployed bridge replaces the temporary tunnel. | npm run phone:self-test:ingest && npm run test:phone-self-test-ingest | pages/cloud-bootstrap.html |  | npm run phone:self-test:ingest && npm run test:phone-self-test-ingest | Do not clear the physical-phone gate from web-surface evidence; it must come from the installed Android app.

## Setup Wizard
Lane | Requirement | Owner | DashboardField | CurrentValue | ValueStatus | UploadSlot | FilesInSlot | NextStep
Business Legal | Attorney/accountant review approved for paid beta | User | billingRehearsal.attorneyReviewStatus | Not approved | Needs input | legal-review | 0 | Mark Approved only after attorney/accountant review clears paid beta.
Payments Licensing | Billing rehearsal mode set to live for final money preflight | User + Codex | billingRehearsal.mode | test | Needs input | stripe-screenshots | 0 | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass.
Release Ops | Paid beta installer is signed or store-trusted | User + Codex | releasePackage.signingStatus | Unsigned internal alpha evidence only | Saved | code-signing | 0 | Upload or generate signed/store-trusted release evidence after the signing path is chosen.

## Agent Dispatch
Department | Status | Cadence | CurrentAssignment | NextAction | BlockerCount | Reads | Writes | SafeCommands
Command Center Intake | WAITING_ON_HANDOFFS | Daily 8:15 AM | Automation Loop | Keep the command center, daily brief, agent dispatch pack, and build queues current until paid launch gates clear. | 85 | daily-command-brief.json, command-center-state.json | handoff-readiness.json ¦ handoff-delta-pack.json ¦ handoff-action-pack.json ¦ daily-command-brief.json ¦ team_updates.csv | npm run intake:scan ¦ npm run handoff:delta ¦ npm run handoff:pack ¦ npm run daily:brief
NyrA Builder | WAITING_ON_HANDOFFS | Every 6 hours | Windows installer version | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear | 70 | daily-command-brief.json, command-center-state.json | src/ ¦ electron/ ¦ docs/release/ ¦ launch_todos.csv ¦ team_updates.csv | npm run model:benchmark:refresh ¦ npm run test:model-benchmark ¦ npm run release:candidate:preflight ¦ npm run test:release-candidate-preflight ¦ npm run command-center:build
Cloud Platform | WAITING_ON_HANDOFFS | Daily 2:30 PM | sync non secret config | Apply saved non-secret dashboard values to production Worker configs and verify the mobile bridge bootstrap plan. | 82 | daily-command-brief.json, command-center-state.json | cloud/command-center-worker/ ¦ cloud/command-center-pages/ ¦ cloud-bootstrap-pack.json ¦ cloudflare-handoff-discovery.json ¦ cloud-deploy-pack.json ¦ team_updates.csv | npm run cloudflare:discover ¦ npm run cloud:bootstrap:pack ¦ npm run cloud:command-center:deploy:preflight ¦ npm run cloud:command-center:deploy:pack ¦ npm run cloud:command-center:pages:check
Mobile Bridge | WAITING_ON_HANDOFFS | Every 6 hours | Hosted alpha phone test stays green | Run npm run alpha:hosted:check before phone testing; 4/4 providers ready, APK 0.1.0-alpha.83, download hash matches manifest, support log readback passed (2026-07-17T04-53-44-939Z-4ef1c4c3-4c15-45d9-80ac-4a7365b366d2). | 3 | daily-command-brief.json, command-center-state.json | cloud/mobile-bridge-worker/ ¦ docs/HOSTED_UPDATES_AND_LOGS.md ¦ docs/launch_command_center/cloud-mobile-bridge.html ¦ team_updates.csv | npm run alpha:hosted:check ¦ npm run test:hosted-alpha-control ¦ npm run cloud:mobile-bridge:check ¦ npm run test:cloud-mobile-bridge ¦ npm run test:mobile-runtime-bridge-status ¦ npm run test:android-alpha-release
Payments Licensing | WAITING_ON_HANDOFFS | Daily | Shipping visuals | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | 62 | daily-command-brief.json, command-center-state.json | payment-launch-pack.json ¦ server/ ¦ cloud/billing-worker/ ¦ team_updates.csv | npm run payment:launch-pack ¦ npm run test:payment-launch-pack ¦ npm run billing:live-preflight -- --mode test --allow-blocked
Secret Store Ops | WAITING_ON_HANDOFFS | Daily | sync non secret config | Apply saved non-secret dashboard values to production Worker configs and verify the mobile bridge bootstrap plan. | 75 | daily-command-brief.json, command-center-state.json | secret-store-pack.json ¦ SECRET_STORE_PACK.md ¦ team_updates.csv | npm run secret:pack ¦ npm run test:secret-pack ¦ npm run daily:brief
Marketing Visuals | WAITING_ON_HANDOFFS | Daily | Shipping visuals | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | 60 | daily-command-brief.json, command-center-state.json | visual-production-pack.json ¦ MARKETING_CAMPAIGN_KIT.md ¦ docs/launch_site/ ¦ team_updates.csv | npm run visuals:pack ¦ npm run marketing:kit ¦ npm run test:visual-production-pack
QA Release | WAITING_ON_HANDOFFS | Daily | Windows installer version | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear | 31 | daily-command-brief.json, command-center-state.json | release-trust-pack.json ¦ release-candidate-preflight.json ¦ QA_LAUNCH_MATRIX.md ¦ team_updates.csv | npm run release:trust:pack ¦ npm run release:candidate:preflight ¦ npm run test:qa-launch-matrix
Version Control | WAITING_ON_HANDOFFS | Daily | App version path | Use the App Version page to record any required mobile companion boundaries or app-store goals. | 35 | daily-command-brief.json, command-center-state.json | version-control-pack.json ¦ VERSION_CONTROL_PACK.md ¦ team_updates.csv | npm run version:control-pack ¦ npm run test:version-control-pack ¦ npm run daily:brief
Business Legal | WAITING_ON_HANDOFFS | Daily | Shipping visuals | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | 50 | daily-command-brief.json, command-center-state.json | legal policy drafts ¦ handoff-action-pack.json ¦ team_updates.csv | npm run deployability:preflight ¦ npm run handoff:pack ¦ npm run test:policy-readiness
Support Ops | WAITING_ON_HANDOFFS | Daily | Redacted support diagnostics export exists | Keep Settings diagnostics export available and redacted before every release candidate. | 46 | daily-command-brief.json, command-center-state.json | support-ops-pack.json ¦ SUPPORT_OPS_PACK.md ¦ docs/support/ ¦ support command-center page ¦ team_updates.csv | npm run support:ops-pack ¦ npm run test:support-ops-pack ¦ npm run test:support-readiness ¦ npm run test:support-diagnostics-runtime ¦ npm run payment:launch-pack
Product Program | WAITING_ON_HANDOFFS | Daily | Daily command-center intake | Automation inventory now verifies required NyrA Codex automations are real and active; daily agents read the Today Command Brief, Decision Recommendations, Handoff Routing Rehearsal, Handoff Action Pack, Agent Dispatch Pack, Dashboard and Collaboration answers, uploads, notes, handoff readiness, deployability blockers, release-candidate status, cloud state, marketing kit, visual status, route newly cleared work, and keep Cloudflare discovery limited to real config drift instead of already-saved D1/R2 handoffs | 59 | daily-command-brief.json, command-center-state.json | pages/decision-recommendations.html | npm run daily:brief ¦ npm run source:truth ¦ npm run command-center:build
Engineering Security | WAITING_ON_HANDOFFS | Daily | Draft privacy policy | Privacy draft now covers mic camera screen memory passive logs third-party AI billing support cloud dashboard provider flows export/delete consent and breach posture | 12 | daily-command-brief.json, command-center-state.json | pages/release-gates.html | npm run test:typed-ipc-gates ¦ npm run test:high-impact-gates ¦ npm run test:privacy-consent-gates
Privacy Consent | WAITING_ON_HANDOFFS | Daily | Draft privacy policy | Privacy draft now covers mic camera screen memory passive logs third-party AI billing support cloud dashboard provider flows export/delete consent and breach posture | 9 | daily-command-brief.json, command-center-state.json | pages/policies.html | npm run test:privacy-consent-gates ¦ npm run test:privacy-consent-runtime ¦ npm run test:policy-readiness
Release Ops | WAITING_ON_HANDOFFS | Daily | Windows installer version | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear | 30 | daily-command-brief.json, command-center-state.json | pages/release-package.html | npm run release:candidate:preflight ¦ npm run test:release-candidate-preflight ¦ npm run test:qa-launch-matrix
Marketing Campaign | WAITING_ON_HANDOFFS | Daily | Final shipping screenshots and demo assets | Storyboards and shot lists are ready; product demo and ad videos wait for final UI, pricing, billing, support, policy URLs, and screenshots. | 59 | daily-command-brief.json, command-center-state.json | pages/marketing.html | npm run public:launch-config ¦ npm run marketing:kit ¦ npm run test:public-launch-config
Visual Assets | WAITING_ON_HANDOFFS | Daily | Final shipping screenshots and demo assets | Storyboards and shot lists are ready; product demo and ad videos wait for final UI, pricing, billing, support, policy URLs, and screenshots. | 16 | daily-command-brief.json, command-center-state.json | pages/visuals.html | npm run visuals:pack ¦ npm run test:visual-production-pack ¦ npm run command-center:build
QA Test | WAITING_ON_HANDOFFS | Daily | Billing live rehearsal | Guarded preflight and rehearsal scripts plus command-center Billing Rehearsal page now check Stripe key mode, required webhook events, Customer Portal/support/legal blockers, HTTPS URLs, no repo secrets, and live-mode safety flag before checkout is exposed | 51 | daily-command-brief.json, command-center-state.json | pages/qa-matrix.html | npm run test:qa-launch-matrix ¦ npm run test:command-center ¦ npm run build:clean

## Handoff Delta
ChangeType | Id | Lane | Owner | PreviousReadiness | CurrentReadiness | CurrentValueStatus | CurrentValueSummary | UploadSlot | CurrentFilesInSlot | SecretStatus | DashboardField | NextStep
No changed handoffs since previous baseline |  |  |  |  | Handoff Delta No Changes | [6 empty] | Run npm run handoff:delta after saving answers or uploading files

## Handoff Rehearsal
Id | Lane | Owner | Readiness | DashboardField | CurrentValueStatus | CurrentValueSummary | UploadSlot | FilesInSlot | SecretStatus | NextStep
legal-review | Business Legal | User | Ready for Codex review | billingRehearsal.attorneyReviewStatus | Saved | Approved | legal-review | 1 |  | Mark Approved only after attorney/accountant review clears paid beta.
billing-live-mode | Payments Licensing | User + Codex | Ready for Codex review | billingRehearsal.mode | Saved | live | stripe-screenshots | 1 |  | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass.
signed-release | Release Ops | User + Codex | Ready for Codex review | releasePackage.signingStatus | Saved | Signed paid beta rehearsal evidence uploaded | code-signing | 1 |  | Upload or generate signed/store-trusted release evidence after the signing path is chosen.
current-screenshots | Visual Assets | Codex | Codex queued | visualProduction.finalScreenshotsApproved | Saved | Yes | product-screenshots | 1 |  | Capture and approve current product screenshots after the shipping UI and billing/support flows are final.

## Collab Workbench
TaskId | Lane | Owner | Requirement | EnterAnswerField | CurrentValue | ValueStatus | LoadFileSlot | FilesInSlot | NextStep | RouteAfterSave
legal-review | Business Legal | User | Attorney/accountant review approved for paid beta | billingRehearsal.attorneyReviewStatus | Not approved | Needs input | legal-review | 0 | Mark Approved only after attorney/accountant review clears paid beta. | Save answers, scan handoffs, then daily agents route cleared work.
billing-live-mode | Payments Licensing | User + Codex | Billing rehearsal mode set to live for final money preflight | billingRehearsal.mode | test | Needs input | stripe-screenshots | 0 | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass. | Save answers, scan handoffs, then daily agents route cleared work.
signed-release | Release Ops | User + Codex | Paid beta installer is signed or store-trusted | releasePackage.signingStatus | Unsigned internal alpha evidence only | Saved | code-signing | 0 | Upload or generate signed/store-trusted release evidence after the signing path is chosen. | Save answers, scan handoffs, then daily agents route cleared work.

## Collaboration Workspace
Section | Department | Owner | Status | FieldLabel | DashboardField | Control | Required | CurrentValueStatus | UploadSlots | CodexAfter
Daily Build Intake | Command Center Intake | User + Codex | Ready for Codex review | Latest user decision | intake.userDecisionSummary | textarea | Yes | Saved | qa-evidence | Run intake scan, handoff delta, daily brief, and agent dispatch; then continue the next unblocked NyrA build task.
Daily Build Intake | Command Center Intake | User + Codex | Ready for Codex review | Next thing you want built | intake.requestedNextBuild | textarea | No | Saved | qa-evidence | Run intake scan, handoff delta, daily brief, and agent dispatch; then continue the next unblocked NyrA build task.
Daily Build Intake | Command Center Intake | User + Codex | Ready for Codex review | Can Codex continue without waiting? | intake.codexCanProceed | select | Yes | Saved | qa-evidence | Run intake scan, handoff delta, daily brief, and agent dispatch; then continue the next unblocked NyrA build task.
Daily Build Intake | Command Center Intake | User + Codex | Ready for Codex review | Notes for Codex | notesForCodex | textarea | No | Saved | qa-evidence | Run intake scan, handoff delta, daily brief, and agent dispatch; then continue the next unblocked NyrA build task.
Business, LLC, Tax | Business Legal | User | Partially filled | Business name | decisions.businessName | text | Yes | Saved | llc-documents ¦ ein-confirmation ¦ legal-review | Update policy drafts, Stripe identity requirements, launch checklist, and deployability gates after evidence is saved.
Business, LLC, Tax | Business Legal | User | Partially filled | Entity path | decisions.entityPath | select | Yes | Saved | llc-documents ¦ ein-confirmation ¦ legal-review | Update policy drafts, Stripe identity requirements, launch checklist, and deployability gates after evidence is saved.
Business, LLC, Tax | Business Legal | User | Partially filled | LLC filed date | decisions.llcFiledDate | date | No | Needs input | llc-documents ¦ ein-confirmation ¦ legal-review | Update policy drafts, Stripe identity requirements, launch checklist, and deployability gates after evidence is saved.
Business, LLC, Tax | Business Legal | User | Partially filled | SC filing ID | decisions.scFilingId | text | No | Needs input | llc-documents ¦ ein-confirmation ¦ legal-review | Update policy drafts, Stripe identity requirements, launch checklist, and deployability gates after evidence is saved.
Business, LLC, Tax | Business Legal | User | Partially filled | EIN status | decisions.einStatus | select | Yes | Needs decision | llc-documents ¦ ein-confirmation ¦ legal-review | Update policy drafts, Stripe identity requirements, launch checklist, and deployability gates after evidence is saved.
Business, LLC, Tax | Business Legal | User | Partially filled | Tax decision | decisions.taxDecision | select | Yes | Saved | llc-documents ¦ ein-confirmation ¦ legal-review | Update policy drafts, Stripe identity requirements, launch checklist, and deployability gates after evidence is saved.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Public product name | decisions.publicProductName | text | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Stripe account mode | decisions.stripeAccountMode | select | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Monthly subscription price cents | decisions.monthlyPriceCents | number | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Hosted AI cap | decisions.hostedAiCap | text | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Refund policy stance | decisions.refundPolicy | text | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Trial policy | decisions.trialPolicy | text | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | BYOK timing | decisions.byokTiming | text | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Billing backend URL | billingRehearsal.backendBaseUrl | url | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Pricing, Stripe, Payments | Payments Licensing | User + Codex | Ready for Codex review | Customer Portal configured | billingRehearsal.customerPortalConfigured | select | Yes | Saved | stripe-screenshots ¦ cloud-handoff | Regenerate pricing model, payment launch pack, billing rehearsal, and Stripe setup commands without storing raw secrets.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | Cloud provider target | decisions.cloudProvider | text | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | Cloud status | decisions.cloudStatus | text | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | Cloud account ready | cloudMigration.accountReady | select | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | Cloud admin email | cloudMigration.adminEmail | email | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | Cloud access decision | cloudMigration.accessDecision | select | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | Dashboard domain/subdomain | cloudMigration.dashboardDomain | text | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | D1 database ID | cloudMigration.d1DatabaseId | text | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | R2 upload bucket | cloudMigration.r2Bucket | text | Yes | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
Cloud Control Room | Cloud Platform | User + Codex | Ready for Codex review | Cloud notes | cloudMigration.notes | textarea | No | Saved | cloud-handoff ¦ domain-email | Sync non-secret Worker config, prepare Pages artifact, update D1/R2 targets, and verify push/pull/scan roundtrip.
App Version And Mobile | QA Release | User + Codex | Ready for Codex review | Publisher name | appVersion.publisherName | text | Yes | Saved | code-signing ¦ mobile-app | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary.
App Version And Mobile | QA Release | User + Codex | Ready for Codex review | Next app version | appVersion.nextVersion | text | Yes | Saved | code-signing ¦ mobile-app | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary.
App Version And Mobile | QA Release | User + Codex | Ready for Codex review | Release target | appVersion.releaseTarget | text | Yes | Saved | code-signing ¦ mobile-app | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary.
App Version And Mobile | QA Release | User + Codex | Ready for Codex review | Release channel | decisions.releaseChannel | select | Yes | Saved | code-signing ¦ mobile-app | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary.
App Version And Mobile | QA Release | User + Codex | Ready for Codex review | Code signing decision | decisions.codeSigningDecision | select | Yes | Saved | code-signing ¦ mobile-app | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary.
App Version And Mobile | QA Release | User + Codex | Ready for Codex review | Mobile target | appVersion.mobileTarget | select | Yes | Saved | code-signing ¦ mobile-app | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary.
App Version And Mobile | QA Release | User + Codex | Ready for Codex review | Mobile companion boundary | appVersion.mobileCompanionBoundary | textarea | Yes | Saved | code-signing ¦ mobile-app | Update version roadmap, release candidate preflight, QA matrix, release notes, and mobile boundary.
Visual Production | Marketing Visuals | Codex + User approval | Partially filled | Hero screenshot status | visualProduction.heroScreenshotStatus | text | Yes | Saved | product-screenshots ¦ marketing-assets ¦ demo-video-assets ¦ stripe-screenshots | Refresh screenshots, demo storyboard, launch-site visuals, ad variants, and final approval checklist.
Visual Production | Marketing Visuals | Codex + User approval | Partially filled | Final screenshots approved | visualProduction.finalScreenshotsApproved | select | Yes | Needs decision | product-screenshots ¦ marketing-assets ¦ demo-video-assets ¦ stripe-screenshots | Refresh screenshots, demo storyboard, launch-site visuals, ad variants, and final approval checklist.
Visual Production | Marketing Visuals | Codex + User approval | Partially filled | Demo video status | visualProduction.demoVideoStatus | text | Yes | Saved | product-screenshots ¦ marketing-assets ¦ demo-video-assets ¦ stripe-screenshots | Refresh screenshots, demo storyboard, launch-site visuals, ad variants, and final approval checklist.
Visual Production | Marketing Visuals | Codex + User approval | Partially filled | Launch site status | visualProduction.launchSiteStatus | text | Yes | Saved | product-screenshots ¦ marketing-assets ¦ demo-video-assets ¦ stripe-screenshots | Refresh screenshots, demo storyboard, launch-site visuals, ad variants, and final approval checklist.
Visual Production | Marketing Visuals | Codex + User approval | Partially filled | Visual notes | visualProduction.notes | textarea | No | Saved | product-screenshots ¦ marketing-assets ¦ demo-video-assets ¦ stripe-screenshots | Refresh screenshots, demo storyboard, launch-site visuals, ad variants, and final approval checklist.
Version Control And Release History | Version Control | User + Codex | Partially filled | Source-control decision | versionControl.sourceControlDecision | select | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Git install status | versionControl.gitInstallStatus | select | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Repo provider | versionControl.repoProvider | select | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Repo owner | versionControl.repoOwner | text | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Repo name | versionControl.repoName | text | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Repo remote URL | versionControl.repoRemoteUrl | url | Yes | Needs input | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | CI provider | versionControl.ciProvider | select | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Release branch strategy | versionControl.releaseBranchStrategy | text | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Tag strategy | versionControl.tagStrategy | text | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Version Control And Release History | Version Control | User + Codex | Partially filled | Backup/archive path | versionControl.backupPath | text | Yes | Saved | version-control | Refresh Version Control Pack, Daily Brief, Agent Dispatch, release evidence, QA matrix, and CI/release docs.
Support, Policies, Public Web | Support Ops | User + Codex | Partially filled | Support email | decisions.supportEmail | email | Yes | Saved | domain-email ¦ legal-review ¦ support-roundtrip | Update support docs, launch site config, public policy links, Customer Portal messaging, and support readiness checks.
Support, Policies, Public Web | Support Ops | User + Codex | Partially filled | Public domain | decisions.domain | text | Yes | Saved | domain-email ¦ legal-review ¦ support-roundtrip | Update support docs, launch site config, public policy links, Customer Portal messaging, and support readiness checks.
Support, Policies, Public Web | Support Ops | User + Codex | Partially filled | Support inbox confirmed | billingRehearsal.supportInboxConfirmed | select | Yes | Saved | domain-email ¦ legal-review ¦ support-roundtrip | Update support docs, launch site config, public policy links, Customer Portal messaging, and support readiness checks.
Support, Policies, Public Web | Support Ops | User + Codex | Partially filled | Attorney review status | billingRehearsal.attorneyReviewStatus | select | Yes | Needs decision | domain-email ¦ legal-review ¦ support-roundtrip | Update support docs, launch site config, public policy links, Customer Portal messaging, and support readiness checks.
Automation Loop | Agent Dispatch | Codex | Tracking | Requested next build | intake.requestedNextBuild | textarea | No | Saved | qa-evidence ¦ cloud-handoff | Keep the command center, daily brief, agent dispatch pack, and build queues current until paid launch gates clear.
Automation Loop | Agent Dispatch | Codex | Tracking | Last user review date | intake.lastReviewedByUser | date | No | Saved | qa-evidence ¦ cloud-handoff | Keep the command center, daily brief, agent dispatch pack, and build queues current until paid launch gates clear.
Automation Loop | Agent Dispatch | Codex | Tracking | Cloud API URL | cloudMigration.commandCenterApiUrl | url | No | Needs input | qa-evidence ¦ cloud-handoff | Keep the command center, daily brief, agent dispatch pack, and build queues current until paid launch gates clear.
Automation Loop | Agent Dispatch | Codex | Tracking | Automation notes | cloudMigration.automationNotes | textarea | No | Needs input | qa-evidence ¦ cloud-handoff | Keep the command center, daily brief, agent dispatch pack, and build queues current until paid launch gates clear.

## Daily Standup
Section | Priority | Owner | Lane | Title | Status | Action | DashboardPage | DashboardField | UploadSlot
Standup Signal | P1 | Codex | Command Center | Today Command Brief freshness | 0h old | Fresh enough for the daily build loop. | pages/brief.html
Standup Signal | P1 | Codex | Command Center | Agent Dispatch freshness | 0h old | Agent assignments are current. | pages/agents.html
Standup Signal | P1 | Codex | Command Center | Source Of Truth Map coverage | 0 missing routes | Every launch blocker has a dashboard route and agent owner. | pages/source-of-truth.html
Standup Signal | P0 | Codex | Command Center | Daily automation inventory | Automations Paused By Operator | Fix missing or inactive NyrA automations before relying on the daily team. | pages/agents.html
Standup Signal | P1 | User | Command Center | User review checkpoint | 10938h old | User review date is saved. | pages/collaboration.html | intake.lastReviewedByUser
User Handoff | P0 | User | Business Legal | Attorney/accountant review approved for paid beta | Waiting on user | Mark Approved only after attorney/accountant review clears paid beta. | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | legal-review
User Handoff | P0 | User + Codex | Payments Licensing | Billing rehearsal mode set to live for final money preflight | Waiting on user | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass. | pages/billing-rehearsal.html | billingRehearsal.mode | stripe-screenshots
User Handoff | P0 | User + Codex | Release Ops | Paid beta installer is signed or store-trusted | Waiting on user | Upload or generate signed/store-trusted release evidence after the signing path is chosen. | pages/release-package.html | releasePackage.signingStatus | code-signing
User Handoff | P0 | User | Business Legal | Business name candidate | Saved matches recommendation | Confirm the final legal/business name, save it in the dashboard, and upload sanitized filing evidence when available. | pages/collaboration.html | decisions.businessName
User Handoff | P0 | User | Business Legal | Entity path | Saved matches recommendation | Choose SC LLC or another documented entity path, then save the decision and upload the filing or accountant/legal note. | pages/collaboration.html | decisions.entityPath
User Handoff | P0 | User | Business Legal | Tax collection/accounting path | Saved matches recommendation | Choose Stripe Tax now, accountant first, or SC-only beta in the dashboard. Get accountant/legal review before live public charging. | pages/collaboration.html | decisions.taxDecision
User Handoff | P0 | User | Payments Licensing | Monthly subscription price | Saved matches recommendation | Save the approved monthly price in cents before creating the Stripe Price. | pages/pricing.html | decisions.monthlyPriceCents
User Handoff | P0 | User | Payments Licensing | Hosted AI cap | Saved matches recommendation | Save the customer-facing hosted AI cap and over-cap behavior before checkout copy is published. | pages/pricing.html | decisions.hostedAiCap
User Handoff | P0 | User | Support Ops | Support inbox | Saved matches recommendation | Confirm you own the inbox, send a test ticket, reply, then mark billingRehearsal.supportInboxConfirmed as Yes. | pages/support.html | decisions.supportEmail
User Handoff | P0 | User | Business Legal | Refund and cancellation policy | Suggested - not saved | Have the refund/cancellation language reviewed before paid launch and upload legal review evidence. | pages/refund-cancellation.html | policy.review.refundCancellation
Secret Store | P0 | User | Stripe Billing | STRIPE_SECRET_KEY | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell. Setup command placeholder: npx wrangler secret put STRIPE_SECRET_KEY --cwd cloud/billing-worker --env production ¦ $env:STRIPE_SECRET_KEY = "<STRIPE_SECRET_KEY>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: STRIPE_SECRET_KEY | cloud-handoff
Secret Store | P0 | User | Stripe Billing | STRIPE_WEBHOOK_SECRET | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell. Setup command placeholder: npx wrangler secret put STRIPE_WEBHOOK_SECRET --cwd cloud/billing-worker --env production ¦ $env:STRIPE_WEBHOOK_SECRET = "<STRIPE_WEBHOOK_SECRET>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: STRIPE_WEBHOOK_SECRET | cloud-handoff
Secret Store | P0 | User | Stripe Billing | NYRA_STRIPE_PRICE_PRO_MONTHLY | Secret-store only | Cloudflare billing Worker secret and temporary billing rehearsal shell. Setup command placeholder: npx wrangler secret put NYRA_STRIPE_PRICE_PRO_MONTHLY --cwd cloud/billing-worker --env production ¦ $env:NYRA_STRIPE_PRICE_PRO_MONTHLY = "<NYRA_STRIPE_PRICE_PRO_MONTHLY>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_STRIPE_PRICE_PRO_MONTHLY | cloud-handoff
Secret Store | P0 | User | NyrA Billing | NYRA_BILLING_SUCCESS_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable. Setup command placeholder: npx wrangler secret put NYRA_BILLING_SUCCESS_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_SUCCESS_URL = "<NYRA_BILLING_SUCCESS_URL>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_SUCCESS_URL | cloud-handoff
Secret Store | P0 | User | NyrA Billing | NYRA_BILLING_CANCEL_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable. Setup command placeholder: npx wrangler secret put NYRA_BILLING_CANCEL_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_CANCEL_URL = "<NYRA_BILLING_CANCEL_URL>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_CANCEL_URL | cloud-handoff
Secret Store | P0 | User | NyrA Billing | NYRA_BILLING_RETURN_URL | Secret-store only | Cloudflare billing Worker secret or hosted backend environment variable. Setup command placeholder: npx wrangler secret put NYRA_BILLING_RETURN_URL --cwd cloud/billing-worker --env production ¦ $env:NYRA_BILLING_RETURN_URL = "<NYRA_BILLING_RETURN_URL>". Verify with npm run billing:live-preflight -- --mode test --allow-blocked. | pages/cloud-billing.html | deployment secret store: NYRA_BILLING_RETURN_URL | cloud-handoff
Secret Store | P0 | User | NyrA License | NYRA_LICENSE_API_TOKEN | Secret-store only | Cloudflare billing Worker secret and desktop activation configuration. Setup command placeholder: npx wrangler secret put NYRA_LICENSE_API_TOKEN --cwd cloud/billing-worker --env production ¦ $env:NYRA_LICENSE_API_TOKEN = "<NYRA_LICENSE_API_TOKEN>". Verify with npm run cloud:billing:check && npm run test:cloud-billing-worker. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_API_TOKEN | cloud-handoff
Secret Store | P0 | User | NyrA License | NYRA_LICENSE_SIGNING_SECRET | Secret-store only | Cloudflare billing Worker and mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/billing-worker --env production ¦ npx wrangler secret put NYRA_LICENSE_SIGNING_SECRET --cwd cloud/mobile-bridge-worker --env production. Verify with npm run cloud:billing:check && npm run test:cloud-billing-worker && npm run cloud:mobile-bridge:check. | pages/cloud-billing.html | deployment secret store: NYRA_LICENSE_SIGNING_SECRET | cloud-handoff
Secret Store | P0 | User | NyrA Mobile Bridge | NYRA_MOBILE_BRIDGE_TOKEN | Secret-store only | Cloudflare mobile bridge Worker secret and temporary bridge test shell. Setup command placeholder: npx wrangler secret put NYRA_MOBILE_BRIDGE_TOKEN --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_MOBILE_BRIDGE_TOKEN = "<NYRA_MOBILE_BRIDGE_TOKEN>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_MOBILE_BRIDGE_TOKEN | cloud-handoff
Secret Store | P1 | User | NyrA Mobile Bridge | NYRA_OPENAI_API_KEY | Secret-store only | Cloudflare mobile bridge Worker secret. Setup command placeholder: npx wrangler secret put NYRA_OPENAI_API_KEY --cwd cloud/mobile-bridge-worker --env production ¦ $env:NYRA_OPENAI_API_KEY = "<NYRA_OPENAI_API_KEY>". Verify with npm run cloud:mobile-bridge:check && npm run test:mobile-bridge-security. | pages/cloud-mobile-bridge.html | deployment secret store: NYRA_OPENAI_API_KEY | cloud-handoff
Codex Build Queue | P0 | Codex | Release | Windows installer version | Active | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear
Codex Build Queue | P1 | Codex | Marketing | Demo video | Active | Storyboards shot lists captions recording checklist and demo/ad scenes now exist; final recording waits for final UI pricing billing support policy URLs and screenshots
Codex Build Queue | P0 | Codex | Product Program | Daily command-center intake | Active | Automation inventory now verifies required NyrA Codex automations are real and active; daily agents read the Today Command Brief, Decision Recommendations, Handoff Routing Rehearsal, Handoff Action Pack, Agent Dispatch Pack, Dashboard and Collaboration answers, uploads, notes, handoff readiness, deployability blockers, release-candidate status, cloud state, marketing kit, visual status, route newly cleared work, and keep Cloudflare discovery limited to real config drift instead of already-saved D1/R2 handoffs
Codex Build Queue | P0 | Codex | Payments/Product | Pricing and hosted AI cap model | Ready | Pricing model script docs snapshot CSV and command-center Pricing page estimate Stripe fees provider token cost support/infra/refund reserves target margin minimum price and recommended hosted AI cap
Codex Build Queue | P0 | Codex | Payments | Create Stripe product/price | Ready | Use billing:stripe-setup after price and Stripe key are ready
Codex Build Queue | P0 | Codex | Payments/QA | Billing live rehearsal | Ready | Guarded preflight and rehearsal scripts plus command-center Billing Rehearsal page now check Stripe key mode, required webhook events, Customer Portal/support/legal blockers, HTTPS URLs, no repo secrets, and live-mode safety flag before checkout is exposed
Codex Build Queue | P0 | Codex | Payments/QA | Payment Launch Pack | Ready | Payment Launch Pack now generates JSON CSV Markdown dashboard workbook Today Brief queue Stripe product/price setup sequence Customer Portal/webhook/backend/secret-store actions test rehearsal commands and live-payment no-go rules
Codex Build Queue | P0 | Codex | Engineering | Deploy billing backend | Ready | Standalone Node 24 billing backend deploy pack and Cloudflare Worker/D1 billing path are ready with manifests checklists health checks required secret lists route coverage storage probes entitlement writes idempotent webhook handling and test:billing-deploy/test:billing-storage/cloud:billing:check/test:cloud-billing-worker; actual hosted deployment still needs domain host or Worker URL D1 database ID secrets Stripe webhook Customer Portal price hosted AI cap support inbox and persistent managed storage
Codex Build Queue | P0 | Codex | Payments/Cloud | Cloud billing Worker/D1 | Ready | Cloudflare Worker nyra-billing-api implements Stripe-hosted Checkout Customer Portal webhooks license status checkout-session claim device-scoped access tokens D1 entitlement/customer/event/device storage and local route tests; live use still needs Cloudflare account D1 database ID Worker URL Stripe test/live secrets price webhook endpoint support email legal URLs and dashboard origin
Codex Build Queue | P0 | User | 1. Public Support Identity | Support email saved | Ready | Save the support address customers will see in the app, Stripe receipts, public policies, and launch site. | pages/support.html | decisions.supportEmail | domain-email
Codex Build Queue | P0 | User | 1. Public Support Identity | Support inbox ticket roundtrip confirmed | Ready | Send a test customer email to the support inbox, reply from the inbox, and upload sanitized proof of the roundtrip. | pages/support.html | billingRehearsal.supportInboxConfirmed | support-roundtrip
Codex Build Queue | P0 | User | 2. Public Policy And Domain | Public domain and policy support path saved | Ready | Save the public product domain so privacy, terms, refund, cancellation, support, checkout success, and portal return URLs can match. | pages/support.html | decisions.domain | domain-email
Agent Assignment | P0 | Codex | Command Center Intake | Automation Loop | Waiting On Handoffs | Keep the command center, daily brief, agent dispatch pack, and build queues current until paid launch gates clear. | pages/agents.html
Agent Assignment | P0 | Codex | NyrA Builder | Windows installer version | Waiting On Handoffs | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear | pages/agents.html
Agent Assignment | P0 | Codex | Cloud Platform | sync non secret config | Waiting On Handoffs | Apply saved non-secret dashboard values to production Worker configs and verify the mobile bridge bootstrap plan. | pages/agents.html
Agent Assignment | P0 | Codex | Mobile Bridge | Hosted alpha phone test stays green | Waiting On Handoffs | Run npm run alpha:hosted:check before phone testing; 4/4 providers ready, APK 0.1.0-alpha.83, download hash matches manifest, support log readback passed (2026-07-17T04-53-44-939Z-4ef1c4c3-4c15-45d9-80ac-4a7365b366d2). | pages/agents.html
Agent Assignment | P0 | Codex | Payments Licensing | Shipping visuals | Waiting On Handoffs | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | pages/agents.html
Agent Assignment | P0 | Codex | Secret Store Ops | sync non secret config | Waiting On Handoffs | Apply saved non-secret dashboard values to production Worker configs and verify the mobile bridge bootstrap plan. | pages/agents.html
Agent Assignment | P0 | Codex | Marketing Visuals | Shipping visuals | Waiting On Handoffs | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | pages/agents.html
Agent Assignment | P0 | Codex | QA Release | Windows installer version | Waiting On Handoffs | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear | pages/agents.html
Agent Assignment | P0 | Codex | Version Control | App version path | Waiting On Handoffs | Use the App Version page to record any required mobile companion boundaries or app-store goals. | pages/agents.html
Agent Assignment | P0 | Codex | Business Legal | Shipping visuals | Waiting On Handoffs | Approve final screenshots only after the app UI, support, billing, and consent flows match what will ship. | pages/agents.html

## Todos
Task | Lane | Owner | Priority | Detail | Status
Business name search | Legal/Business | User | P0 | Search SC business filings and USPTO for NyrA/Nyra Swarm/NyrA Little Buddy conflicts | Not started
Choose entity path | Legal/Business | User | P0 | SC LLC path saved as Porter Labs LLC in command center; formation evidence uploaded and filing remains in progress | SC LLC selected
File SC LLC if chosen | Legal/Business | User | P0 | Porter Labs LLC SC registration is in progress via uploaded ZenBusiness evidence; formation date still not issued | In progress
Get EIN | Legal/Business | User | P0 | Apply through IRS after the LLC formation date is issued; current evidence shows EIN not started | Blocked on formation
Open/confirm business bank | Finance | User | P0 | Separate revenue from personal money | Blocked on entity/EIN
Stripe identity/tax setup | Payments | User | P0 | Use Porter Labs LLC and porterlabz.com for Stripe identity after tax decision, price, portal, and legal review clear | Waiting on tax/pricing
Choose monthly price | Payments | User | P0 | Pick first monthly SKU price using the Pricing Model page; model currently supports a $25 planning scenario with payment/provider/support reserves, but final price needs user approval | Open
Choose hosted AI cap | Payments/Product | User | P0 | Define included usage and over-cap behavior using the Pricing Model page; model currently calculates a hosted-message cap from token and margin assumptions because BYOK is later | Open
Pricing and hosted AI cap model | Payments/Product | Codex | P0 | Pricing model script docs snapshot CSV and command-center Pricing page estimate Stripe fees provider token cost support/infra/refund reserves target margin minimum price and recommended hosted AI cap | Ready
Create Stripe product/price | Payments | Codex | P0 | Use billing:stripe-setup after price and Stripe key are ready | Ready
Configure Customer Portal | Payments | User/Codex | P0 | Enable cancellation, invoices, payment methods | Open
Billing live rehearsal | Payments/QA | Codex | P0 | Guarded preflight and rehearsal scripts plus command-center Billing Rehearsal page now check Stripe key mode, required webhook events, Customer Portal/support/legal blockers, HTTPS URLs, no repo secrets, and live-mode safety flag before checkout is exposed | Ready
Payment Launch Pack | Payments/QA | Codex | P0 | Payment Launch Pack now generates JSON CSV Markdown dashboard workbook Today Brief queue Stripe product/price setup sequence Customer Portal/webhook/backend/secret-store actions test rehearsal commands and live-payment no-go rules | Ready
Approve billing backend host and secrets | Payments/Cloud | User | P0 | Choose container host and backend domain, create private secret values, choose an absolute mounted persistent entitlement path or managed database path, then provide webhook URL/secret through the dashboard without committing secrets | Open
Deploy billing backend | Engineering | Codex | P0 | Standalone Node 24 billing backend deploy pack and Cloudflare Worker/D1 billing path are ready with manifests checklists health checks required secret lists route coverage storage probes entitlement writes idempotent webhook handling and test:billing-deploy/test:billing-storage/cloud:billing:check/test:cloud-billing-worker; actual hosted deployment still needs domain host or Worker URL D1 database ID secrets Stripe webhook Customer Portal price hosted AI cap support inbox and persistent managed storage | Ready
Cloud billing Worker/D1 | Payments/Cloud | Codex | P0 | Cloudflare Worker nyra-billing-api implements Stripe-hosted Checkout Customer Portal webhooks license status checkout-session claim device-scoped access tokens D1 entitlement/customer/event/device storage and local route tests; live use still needs Cloudflare account D1 database ID Worker URL Stripe test/live secrets price webhook endpoint support email legal URLs and dashboard origin | Ready
Wire desktop activation | Engineering | Codex | P0 | Settings license panel now supports checkout session activation, refresh, cached grace state, read-only customer ID, and device-token portal access | Ready
Production license auth model | Payments/Engineering | Codex | P0 | Checkout-session claim plus device-scoped access token flow is implemented locally; deploy backend and connect live Stripe webhooks before paid beta | Ready
Draft privacy policy | Legal/Privacy | Codex | P0 | Privacy draft now covers mic camera screen memory passive logs third-party AI billing support cloud dashboard provider flows export/delete consent and breach posture | Ready
Legal policy packet | Legal/Privacy | Codex | P0 | Privacy Terms EULA Refund/Cancellation Security and Legal Review Packet drafts now exist as repo files command-center pages and a Word review packet | Ready
Attorney review | Legal | User | P0 | Review docs/policies drafts and NyrA_Legal_Review_Packet.docx before publishing policies or taking live payments | Open
Create support inbox | Support | User | P0 | Create/confirm nyrasupport@gmail.com or domain email | Open
Support diagnostics and runbook | Support | Codex | P0 | Settings now exposes Export Support Diagnostics with redacted app runtime consent license provider and local-data-count metadata; support runbook covers intake ticket categories diagnostics billing/refund workflow canned replies and no-go conditions; live support still needs inbox ownership and ticket roundtrip | Ready
Buy domain | Marketing/Web | User | P0 | porterlabz.com is saved as the public product and policy domain; DNS and hosted deployment handoffs still pending | Domain saved
Landing page | Marketing/Web | Codex | P0 | Generated local launch site with safe claims, product screenshots, policy links, readiness blockers, and checkout disabled until price hosted AI cap domain support live Stripe and review gates are ready | Ready
Code signing | Release | User/Codex | P0 | Release Trust Decision Form now maps direct signed installer Microsoft Store both-channel and hold-unsigned paths; user still must buy/verify signing certificate or choose Store trust before paid beta | Open
Windows installer version | Release | Codex | P0 | Internal alpha metadata is set to version 0.1.0-alpha.83, appId com.porter.nyra.swarm-little-buddy, product name NyrA Swarm Little Buddy; desktop 0.1.0-alpha.83 evidence SHA256 6852fb9095a426a5c8128225e93d22b0ca3521c51d4d2af605ca3219327ee863; Android 0.1.0-alpha.83 versionCode 83 SHA256 b92bbedcc86066f17edc620a105b04a6cdbd284b6d767abdb1b88ecfb07791b0; release notes known issues rollback manifest checksums installer rehearsal release-trust decision packet and release-candidate preflight are wired; current verdict is Internal Alpha Only until signed/store-trusted installer evidence and paid-beta handoffs clear | Active
Release package evidence | Release | Codex | P0 | Release runbook release notes known issues rollback plan release-manifest and SHA256SUMS generation are wired into clean build; command center release package page renders manifest checksums signing status and blockers | Ready
Clean production build path | Release/QA | Codex | P0 | npm run build:clean copies the repo outside Google Drive, reinstalls dependencies, runs license/billing/production/cloud gates, builds release/0.1.0-alpha.83/win-unpacked/NyrA Swarm Little Buddy.exe, refreshes release evidence, and syncs command-center release metadata for 0.1.0-alpha.83; latest verified desktop evidence remains 0.1.0-alpha.83 until that build passes | Ready
Paid feature entitlement gate | Payments/Engineering | Codex | P0 | Main-process IPC gate now blocks API swarm chat voice realtime screen capture computer control file/app control and developer terminal unless an active cached license remains inside offline grace; denied paid actions return NYRA_PRO_REQUIRED; checkout and activation stay reachable | Ready
Security gates | Engineering | Codex | P0 | Paid entitlement gate, OpenAI storage gate, terminal env gate, main-process high-impact approval enforcement, first-run consent/privacy gates, and typed IPC hardening now exist with static/runtime release gates | Ready
Typed IPC hardening | Engineering Security | Codex | P0 | Preload bridge now uses allowlisted invoke send and listen channels, store-key allowlist, payload shape and size validation, unsafe URL protocol blocking, and sanitized listener events; typed IPC static/runtime tests are wired into clean build | Ready
High-impact action approval gate | Engineering Security | Codex | P0 | Main-process gate returns NYRA_HIGH_IMPACT_APPROVAL_REQUIRED for payment credential account-changing destructive system-setting installer/script data-sharing and developer-terminal risks; normal runs show an Electron approval dialog and automated runs deny deterministically | Ready
Dependency security audit | Engineering Security | Codex | P0 | Upgraded Electron to 42.3.0, electron-builder to 26.8.1, Vite to 8.0.14, Vite React plugin to 6.0.2, and Vite Electron plugins to 1.0.0; clean build now reports 0 npm audit vulnerabilities | Ready
Consent and memory controls | Engineering | Codex | P0 | First-run consent step Settings Privacy & Consent panel NYRA_CONSENT_REQUIRED main-process enforcement local privacy export and memory/log deletion are implemented for mic camera screen computer control third-party AI local memory and passive context log | Ready
QA launch matrix | QA | Codex | P0 | QA launch matrix now maps command-center launch-site billing-deploy license billing paid-feature high-impact privacy-consent typed-IPC policy production cloud Windows package clean-build and targeted computer-use stop/realtime/camera gates; test:qa-launch-matrix verifies scripts docs and build-clean coverage | Ready
Demo video | Marketing | Codex | P1 | Storyboards shot lists captions recording checklist and demo/ad scenes now exist; final recording waits for final UI pricing billing support policy URLs and screenshots | Active
Visual asset readiness inventory | Visual Assets | Codex | P0 | npm run visuals:inventory now tracks 23 screenshots diagrams launch-site assets and video rows across JSON CSV Markdown and the Visuals dashboard, and it prefers the latest available Android evidence instead of alpha46-only pointers; final screenshots remain unapproved until UI billing support and consent flows are frozen | Ready
Ad campaign | Marketing | Codex | P1 | Campaign kit now includes beta invite email sequence social posts ad variants campaign calendar safe claims and publication rules; final publication waits for domain price hosted AI cap checkout URL policy URLs and screenshots | Ready
Daily command-center intake | Product Program | Codex | P0 | Automation inventory now verifies required NyrA Codex automations are real and active; daily agents read the Today Command Brief, Decision Recommendations, Handoff Routing Rehearsal, Handoff Action Pack, Agent Dispatch Pack, Dashboard and Collaboration answers, uploads, notes, handoff readiness, deployability blockers, release-candidate status, cloud state, marketing kit, visual status, route newly cleared work, and keep Cloudflare discovery limited to real config drift instead of already-saved D1/R2 handoffs | Active
Secret store setup pack | Command Center Intake | Codex | P0 | Secret Store Setup now generates JSON CSV Markdown dashboard and workbook rows for Stripe billing Worker license signing command-center bearer token local cloud sync variables safe placeholder-only commands verification commands and no-raw-secret rules | Ready
Dashboard collaboration workspace | Product Program | Codex | P0 | Dashboard now exposes saveable handoff fields, Launch Setup Wizard, Daily Agents page, cloud/app-version/visual state, and command-center collaboration checks so it can function as the shared workspace between user and Codex | Ready
Decision recommendations | Command Center Intake | Codex | P0 | Decision Defaults now generates JSON CSV Markdown dashboard and workbook rows with recommended price hosted AI cap entity path support cloud release signing app-version and visual defaults while explicitly not clearing legal Stripe support cloud signing tax or secret-store handoffs | Ready
Deployability preflight | Product Program | Codex | P0 | Single live-money go/no-go preflight now generates deployability-snapshot.json deployability-blockers.csv DEPLOYABILITY_PREFLIGHT.md dashboard page blocker table action queue and daily-agent evidence from command-center state and environment | Ready
Collaboration handoff console | Command Center Intake | Codex | P0 | Collaboration page renders the live deployability blocker queue as exact user handoffs with dashboard page field upload slot status and next action so decisions and files can be entered in one operating space | Ready
Intake readiness scanner | Command Center Intake | Codex | P0 | npm run intake:scan generates handoff-readiness.json handoff-readiness.csv HANDOFF_READINESS.md and the Handoff Readiness dashboard page from saved fields uploads secret-store presence and deployability blockers | Ready
Command-center state concurrency guard | Command Center Intake | Codex | P0 | Shared command-center JSON writes now use atomic replacement and a lock-backed update path; npm run test:command-center-concurrency verifies overlapping deployability and intake agent runs keep both dashboard status blocks valid | Ready
Cloud dashboard deployment | Cloud Platform | Codex | P0 | Worker API D1 schema R2 upload path cron marker hardened auth JSON/request limits browser cloud connection private Pages dashboard artifact CLI push/pull/scan/roundtrip sync and test harness exist locally; deploy after Cloudflare account/domain/auth approval | Ready
Cloud Deploy Pack | Cloud Platform | Codex | P0 | Cloud Deploy Pack now generates JSON CSV Markdown dashboard workbook Today Brief queue Cloudflare resource targets safe placeholder commands D1/R2/Worker/Pages setup sequence first cloud sync commands and no-secret rules from the cloud deploy preflight | Ready
Cloud command-center sync | Cloud Platform | Codex | P0 | Dashboard can store a Cloud Worker API URL/token in browser localStorage only, save/pull state through the Worker, upload through R2-backed API, scan handoffs, classify Source Of Truth Map routes, record intake runs, and CLI scripts can health/push/pull/source-truth/scan/roundtrip once NYRA_COMMAND_CENTER_API_URL and NYRA_COMMAND_CENTER_TOKEN are set; Worker now validates JSON and upload limits and Pages artifact excludes local uploads/raw state before cloud deployment | Ready
Cloud Pages deploy pack | Cloud Platform | Codex | P0 | cloud/command-center-pages now contains Wrangler Pages config README and a generated public artifact with command-center HTML assets Excel/legal/release links no-index/no-store headers publish manifest and exclusion checks for uploads raw state and local server files | Ready
Approve Cloudflare cloud handoff | Cloud Platform | User | P0 | Confirm Cloudflare account domain/subdomain admin email Cloudflare Access preference and approval to create D1/R2 resources | Open
App version roadmap | Release/Product | Codex | P0 | Maintain editable 0.1.0 alpha/beta, 0.2.0 reliability, 1.0.0 launch, and future mobile companion criteria from dashboard decisions; roadmap source doc dashboard board daily version-agent queue mobile boundary and clean-build check are implemented | Ready
Physical phone bridge self-test evidence review | QA/Mobile Bridge | User/Codex | P0 | Reviewed the ready-for-Codex phone self-test row again on 2026-06-13. The latest saved evidence is NO_PHONE_SELF_TEST_LOG with passed=false, physicalPhone=false, and phone-evidence has 0 uploaded files, so it does not clear the physical-phone gate; keep pages/cloud-mobile-bridge.html, mobileBridge.lastPhoneSelfTest, phone-evidence, and the real phone rerun step visible. | Blocked on physical phone proof

## Costs
Item | Category | Cadence | LowUSD | HighUSD | Notes
SC LLC Articles of Organization | State filing | One-time | 110 | 110 | User files with SC Secretary of State if LLC chosen
SC Retail License | Tax/license | One-time | 0 | 50 | May be needed if taxable retail sales apply; confirm with accountant/SCDOR
IRS EIN | Federal tax ID | One-time | 0 | 0 | Free directly from IRS
Domain | Brand/web | Annual | 10 | 20 | Cloudflare at-cost or registrar of choice
Business email | Support/ops | Monthly | 7 | 14 | Google Workspace Starter/Standard or Gmail workaround
Code signing certificate | Release trust | Annual | 129 | 508 | OV baseline plus possible hardware/cloud signing costs
Stripe processing | Payments | Per transaction | 0 | 0 | Budget 2.9% + 30c domestic online card baseline
Attorney review | Legal | One-time | 500 | 2500 | Privacy/terms/EULA/refund/subscription review
Accountant/tax consult | Tax | One-time | 200 | 750 | Sales tax, entity, bookkeeping, income tax setup
Bookkeeping software | Ops | Monthly | 0 | 35 | Can start spreadsheet, upgrade later
Website hosting | Web | Monthly | 0 | 25 | Cloudflare Pages/static can start free
AI provider budget | COGS | Monthly | 50 | 500 | Required if BYOK is not first launch
Support tooling | Ops | Monthly | 0 | 30 | Start Gmail labels, upgrade to helpdesk later
Design/video tools | Marketing | Monthly | 0 | 50 | Can start with repo assets and free tools

## Team Room
Team | Lead | Status | CurrentFocus | NextOutput | BlockedBy | UpdateCadence | PrimaryArtifact
Product Program | Codex | Active | Keep dashboard-as-command-center source of truth tight and route ready Codex launch work into concrete department assignments instead of passive watch states. | Updated agent dispatch assignments, daily brief routing, and department next actions from the live command-center queue | None | Daily | pages/decision-recommendations.html
Business Legal | User + Codex | Blocked | Porter Labs LLC / SC LLC path is recorded; ZenBusiness evidence shows formation date and EIN still not issued; tax/accountant review remains next. | Formation date, EIN, tax decision, and attorney-accountant approval when available | Formation completion, EIN, tax decision, attorney/accountant review | Weekly | pages/policies.html
Payments Licensing | Codex | Active | Stripe Checkout Customer Portal webhooks entitlement activation customer-safe device activation deploy pack Cloudflare Worker/D1 path pricing/cap planner no-trial entitlement enforcement BYOK-later policy Payment Launch Pack guarded billing live rehearsal preflight and paid-beta storage guard | Use Payment Launch Pack to clear price cap no-trial/BYOK policy Stripe product/price portal webhook backend URL secret-store and test rehearsal actions before hosted billing rehearsal | Monthly price hosted AI cap domain support email Stripe account details Customer Portal webhook secret hosting target Cloudflare D1 database ID and Worker URL | Daily | pages/payment-launch-pack.html
Engineering Security | Codex | Active | Paid-feature entitlement gate terminal gating high-impact approval consent enforcement typed IPC hardening license activation wiring and zero-audit Electron 42 build baseline | Closed P0 security/license/high-impact/privacy/typed-IPC gate evidence | Live deployment signing legal and release-channel decisions | Daily | pages/release-gates.html
Privacy Consent | Codex | Active | First-run and Settings controls for mic camera screen memory passive context logs third-party AI and computer control are implemented and main-process enforced; privacy policy draft and AI provider data-flow draft now map OpenAI Anthropic Gemini xAI/Grok flows | Attorney review of privacy retention provider-data wording and public policy URLs | Attorney review support inbox domain exact retention policy final provider stack and hosted AI cap | Daily | pages/policies.html
Release Ops | User + Codex | Active | 0.1.0-alpha.83 release-candidate preflight now publishes the current Internal Alpha Only vs paid-beta verdict from release evidence, deployability handoffs, cloud automations, marketing visuals, billing, support, legal, Android, and app-version state | Keep release-candidate JSON CSV Markdown Release Package blocker queue and daily release queue current after every dashboard rebuild; current desktop output is C:/Users/porte/OneDrive/Desktop/NyrA/release/0.1.0-alpha.83/win-unpacked/NyrA Swarm Little Buddy.exe | User must choose certificate/store/direct-download path and clear paid-beta handoffs before the verdict can become paid-beta ready | Daily | pages/release-package.html
Support Ops | User + Codex | Active | Support diagnostics export runbook ticket categories refund workflow macros and inbox setup | Support inbox ticket roundtrip after mailbox exists | User must create/confirm support inbox before public support can go live | Daily | pages/support.html
Marketing Campaign | Codex | Active | Campaign kit now contains beta invite email sequence social posts ad variants campaign calendar and demo/ad shot lists plus the generated launch site with safe claims and publishing blockers | Final launch campaign with current screenshots domain price hosted AI cap and checkout URL | Need domain price hosted AI cap final product screenshots policy URLs recorded demo and live Stripe checkout URL | Daily | pages/marketing.html
Visual Assets | Codex | Active | Visual inventory now tracks 23 screenshots diagrams launch-site assets and videos, and the Android evidence route now prefers the latest available alpha71 panel and launch captures instead of stale alpha46-only pointers while final screenshot approval stays blocked until the shipping UI billing support and consent flows freeze | Refresh final paid-beta screenshots and record demo/ad videos after UI and payment/support gates are ready | Need fresh paid-beta screenshots after final UI billing support consent and pricing flows plus an alpha72 Android refresh to clear the remaining stale versioned evidence | Daily | pages/visuals.html
QA Test | Codex | Active | QA launch matrix clean-build release gates and generated-artifact readers now cover command center launch site billing deploy license billing paid features high-impact approvals privacy consent typed IPC policy production cloud Windows package and targeted stop/realtime/camera smokes; the 2026-06-13 phone self-test review still shows NO_PHONE_SELF_TEST_LOG and 0 phone-evidence files, so the physical-phone gate remains blocked even after the intake false-ready regression was removed. | Passing launch gate report from npm run build:clean on 0.1.0-alpha.83 plus current command-center generated-file checks and Android alpha 0.1.0-alpha.83 smoke evidence | Needs a real physical-phone bridge self-test, live Stripe hosted-backend rehearsal, signed release channel support inbox public domain checks, and final nonparallel clean build after handoffs clear | Daily | pages/qa-matrix.html
Command Center Intake | Codex | Active | 2026-06-18 intake still has 0 real Ready-for-Codex rows; Cloudflare discovery now suppresses already-saved D1/R2 review noise and only surfaces true cloud config drift. | Continue daily scans and route only newly changed dashboard answers, uploads, app-version changes, payment/public/cloud changes, secret-store presence, inferred non-secret mobile-bridge defaults, and real Cloudflare drift into department work. | 9 user handoffs, 9 secret-store handoffs, cloud worker URLs/origin/tokens, support, legal, billing, signed-release, final screenshot, and physical-phone evidence gates still block paid launch. | Daily | pages/daily-standup.html
Cloud Platform | Codex | Active | Cloud Worker API D1 schema R2 upload path cron marker auth guard private Pages dashboard Cloud Bootstrap Pack Cloud Deploy Pack deploy preflight Cloudflare billing Worker/D1 path browser cloud connection CLI cloud sync cloud handoff scan parity Source Of Truth Map route parity and deployment hardening are locally scaffolded; Cloudflare discovery now reports only unsaved non-secret drift instead of replaying already-saved D1/R2 resources. | Use Cloud Bootstrap Pack to clear Wrangler login resource creation config sync secret migration deploy source-truth route check and first roundtrip checks before Cloud Deploy Pack production deploys. | Needs Cloudflare account domain Access/admin email command-center Worker URL billing Worker URL dashboard origin temporary sync token and secrets; saved D1/R2 names are no longer the active blocker. | Daily | pages/cloud-bootstrap.html

## Updates
Date | Team | Update | Artifact | Next
2026-06-18 | Command Center Intake | Patched Cloudflare discovery so already-saved non-secret D1 R2 and Worker values no longer come back as Ready for review; daily intake now treats that queue as current until real cloud drift appears. | scripts/discover-cloudflare-handoffs.mjs | Keep intake focused on new dashboard answers uploads secret presence worker URLs origin and any fresh Cloudflare drift instead of replaying saved resource IDs.
2026-06-18 | Cloud Platform | Fixed the Cloudflare handoff discovery classifier and regression suite so the command center only asks for review when discovered Cloudflare values differ from saved state. | docs/cloudflare-handoff-discovery-check.mjs | Rerun npm run cloudflare:discover after Cloudflare resource or deployment changes and only treat newly suggested updates as actionable.
2026-06-01 | Command Center Intake | Added a browser Check Source Map control and local /api/source-of-truth endpoint so the dashboard can verify source-of-truth route coverage from localhost or the deployed Worker | cloud.html | Use Check Source Map after saving handoffs or syncing cloud state so daily agents know whether dashboard fields uploads secrets and Codex routes are current
2026-06-18 | Command Center Intake | Consumed the mobile-bridge-bundled-url Ready for Codex review row by rebuilding Android against the verified stable Worker URL with tokenBundled=false and refreshing launch routing. | release/current/android/manifest.json | Continue from the 9 user handoffs and 9 secret-store handoffs; no real Ready for Codex review rows remain.
2026-06-01 | Cloud Platform | Added cloud Source Of Truth Map parity so the command-center Worker exposes /api/source-of-truth and classifies dashboard fields uploads secret-store rows and Codex routes from synced cloud state | cloud/command-center-worker/src/index.mjs | After Cloudflare handoff run cloud:command-center:push then cloud:command-center:source-truth and cloud:command-center:scan before daily agents trust cloud state
2026-06-01 | Cloud Platform | Added Cloudflare handoff discovery so the dashboard can non-destructively check Wrangler auth D1 R2 Pages and Worker targets then surface redacted non-secret update suggestions | pages/cloudflare-discovery.html | Run npm run cloudflare:discover after Cloudflare login resource creation or deployment before treating cloud handoffs as current
2026-06-01 | Command Center Intake | Hardened the local dashboard API to match cloud safety limits with JSON content-type checks request size caps malformed base64 rejection 10 MB upload cap sanitized upload content types and a temp-server regression test | command-center-server.mjs | Keep using localhost 8891 for fillable handoffs while cloud is pending and run npm run test:command-center-server-security after local API changes
2026-06-01 | Command Center Intake | Added Decision Recommendations so the dashboard proposes safe defaults for price hosted AI cap entity path support cloud release signing app version and visuals without clearing real handoffs | pages/decision-recommendations.html | Use Decision Defaults to save or override launch choices then scan handoffs so daily agents can continue the next unblocked build task
2026-05-31 | Command Center Intake | Added a generated Handoff Wizard start-here page that turns current P0 launch blockers into fillable cards upload slots secret-store warnings save scan record-run controls and backlog routing | pages/handoff-wizard.html | Use the Handoff Wizard first when entering LLC Stripe cloud support release or pricing handoffs
2026-05-31 | Payments Licensing | Added Payment Launch Pack so Stripe product price Customer Portal webhooks billing backend secret-store setup test rehearsal and live-payment no-go rules are one dashboard/workbook queue | pages/payment-launch-pack.html | Use Payment Launch Pack before creating Stripe resources or enabling checkout
2026-05-31 | Cloud Platform | Added Cloud Deploy Pack so the cloud migration now has exact Cloudflare resource targets dashboard handoffs safe command sequence first cloud sync steps and no-secret rules | pages/cloud-deploy-pack.html | Clear Cloudflare account Access domain D1 R2 origin and token handoffs then deploy Pages Worker and run cloud sync roundtrip
2026-05-31 | Command Center Intake | Reordered command-center builds so Handoff Action Pack and Secret Store Setup Pack generate before Today Command Brief and added exact secret setup queue rows to the brief dashboard CSV workbook and checks | pages/brief.html | Use Today Brief as the start-here page after any dashboard handoff or secret-store setup update
2026-05-31 | Command Center Intake | Updated required daily automations and automation inventory checks so agents must run and read the Secret Store Setup Pack before continuing launch work | automation-status.json | Keep automation prompts aligned with Today Brief Handoff Pack Secret Store Pack and no-secret rules
2026-05-31 | Command Center Intake | Added Secret Store Setup Pack with placeholder-only Wrangler commands temporary shell commands no-raw-secret rules verification commands and dashboard workbook output | pages/secret-store.html | Use Secret Store Setup before entering Stripe billing license or command-center cloud sync secrets anywhere
2026-05-31 | Command Center Intake | Added Handoff Action Pack with ordered user actions secret-store actions evidence slots dashboard fields no-secret rules Codex follow-up and workbook sheet | pages/handoff-pack.html | Use Handoff Pack as the fastest checklist for clearing user and secret-store launch blockers
2026-05-31 | Command Center Intake | Added Today Command Brief JSON CSV Markdown dashboard page and Excel sheet so user handoffs Codex work release blocks cloud blocks and visual work start from one operating brief | pages/brief.html | Run npm run daily:brief after any handoff release cloud visual marketing or automation update
2026-05-31 | Release Ops | Added release-candidate preflight that produces JSON CSV Markdown and Release Package dashboard verdict for Internal Alpha Only versus paid-beta readiness | release-candidate-preflight.json | Keep running npm run release:candidate:preflight after release evidence or dashboard handoffs change
2026-05-31 | Release Ops | Added installer rehearsal path with NSIS setup build command manifest installer-artifact evidence and paid-beta signing/store-trust guard | pages/release-package.html | Run npm run release:installer:rehearsal after release-channel and signing/store decision are ready to rehearse the setup artifact
2026-05-31 | Command Center Intake | Added Launch Setup Wizard page and Excel Setup Wizard sheet so all user-owned and secret-store P0 launch blockers are in one fillable workflow | pages/launch-setup.html | Use Launch Setup as the first handoff page for business pricing billing cloud support release and secret-store readiness
2026-05-31 | Payments Licensing | Added Cloudflare Worker and D1 billing API path with Checkout Portal webhooks license status device activation HMAC tokens idempotent webhook storage and local tests | ../../cloud/billing-worker/README.md | Set Cloudflare D1 database ID secrets Worker URL Stripe price portal webhook then run test-mode deploy rehearsal
2026-05-31 | Cloud Platform | Added command-center Cloud Billing page and deploy manifest so the cloud billing backend path is visible in the dashboard and Pages deploy artifact | pages/cloud-billing.html | Wire Cloudflare account details D1 database ID billing Worker URL and secrets into the dashboard before live rehearsal
2026-05-31 | Release Ops | Added release-trust decision workflow with direct signed installer Microsoft Store both-channel and hold-unsigned paths plus dashboard fields for certificate/store evidence | release-trust-plan.json | User chooses release channel and code-signing path then Codex enables the matching signed/store release evidence
2026-05-31 | Cloud Platform | Added Cloudflare Pages dashboard deploy pack with static artifact builder private-dashboard headers Wrangler Pages config and exclusion checks for uploads raw state and local server files | cloud/command-center-pages | Create the Pages project protect it with Cloudflare Access then set Worker ALLOWED_ORIGIN to the Pages origin
2026-05-31 | Cloud Platform | Added cloud /api/intake/scan parity and npm run cloud:command-center:scan so deployed dashboards and daily automations can trigger handoff scans against synced state | cloud/command-center-worker/src/index.mjs | After Cloudflare deployment run cloud push scan and roundtrip before treating cloud as source of truth
2026-05-31 | Command Center Intake | Added browser-triggered handoff scans through /api/intake/scan so Dashboard Collaboration and Handoff Readiness pages can refresh scan/build evidence without terminal commands | command-center-server.mjs | Use Scan Handoffs after saving fields or uploading files to refresh readiness and record an agent run
2026-05-31 | Command Center Intake | Added the intake readiness scanner and dashboard page so saved fields uploads and secret-store presence become machine-readable before daily agents choose work | pages/handoff-readiness.html | Run intake scan during every command-center build and use ready rows to unblock Codex tasks
2026-05-31 | Command Center Intake | Added the deployability handoff evidence rows to the Excel workbook Handoffs sheet so offline tracker users see current values upload counts and next actions | NyrA_Launch_Command_Center.xlsx | Keep the web dashboard and workbook rebuilt from the same queue and state
2026-05-31 | Command Center Intake | Added saved-value and upload-count evidence to the Collaboration handoff console so each deployability blocker shows whether state or files are already present | pages/collaboration.html | Use the console to confirm user handoffs are recognized before daily agents pick build work
2026-05-31 | Command Center Intake | Added the live Launch Handoff Console to the Collaboration page so user-owned deployability blockers show exact page field upload slot and next action | pages/collaboration.html | Use Collaboration as the daily place to enter decisions and upload blocker evidence
2026-05-31 | Command Center Intake | Added deployability-blockers action queue to route every live-money blocker to an exact dashboard page field upload slot status and next step | deployability-blockers.csv | Daily automations now read this queue before choosing build work or reporting user handoffs
2026-05-31 | Product Program | Added deployability preflight that generates one live-money go/no-go verdict JSON report dashboard page and blocker list from command-center state and environment | pages/deployability.html | Use the preflight first each day to route the highest-impact blocker toward paid beta
2026-05-31 | Payments Licensing | Added paid-beta billing entitlement storage guard with atomic JSON writes writable health probe production persistent-path startup guard and command-center validation coverage | server/nyra-billing-server.mjs | Choose hosted billing provider and mounted persistent entitlement path for test-mode deployment rehearsal
2026-05-31 | Cloud Platform | Hardened the Cloudflare command-center Worker with constant-time token auth JSON content-type checks request/upload size caps explicit production D1/R2 bindings nodejs_compat and deploy checklist coverage | cloud/command-center-worker/src/index.mjs | Replace Cloudflare placeholders then run first authenticated cloud deployment rehearsal
2026-05-31 | Payments Licensing | Added guarded billing live rehearsal preflight and command-center page for Stripe mode webhook portal support legal URL and secret readiness | pages/billing-rehearsal.html | Run test-mode hosted billing rehearsal after backend URL and Stripe test secrets exist
2026-05-31 | Payments Licensing | Added pricing and hosted AI cap planner with Stripe/provider cost reserves target-margin math snapshot CSV and dashboard Pricing page | pages/pricing.html | User chooses final monthly price and hosted AI cap before live Stripe product creation
2026-05-31 | Cloud Platform | Added browser-side Cloud Worker connection controls and CLI health push pull roundtrip sync so the command center can move off this computer after deployment | ../../scripts/command-center-cloud-sync.mjs | Deploy Worker and run first authenticated cloud sync after Cloudflare handoff
2026-05-31 | Product Program | Converted command center into a structured dashboard plan with team lanes and data files | index.html | Regenerate pages after every data change
2026-05-31 | Payments Licensing | Billing server and Stripe setup scripts exist and smoke tests passed | ../payments/STRIPE_SETUP_RUNBOOK.md | Need price support email domain and Stripe identity
2026-05-31 | Marketing Campaign | Initial positioning campaign and safe-claims direction created | MARKETING_CAMPAIGN.md | Turn campaign into HTML kit and landing page
2026-05-31 | Visual Assets | Initial business Stripe legal marketing and 90-day diagrams created | visuals/02_stripe_architecture.jpg | Add storyboard and screenshot checklist
2026-05-31 | Business Legal | Entity and legal checklist drafted with source register | sources.csv | User must choose entity path and support/domain identity
2026-05-31 | Command Center Intake | Added live Collaboration page with saveable form state upload slots and rebuild action | pages/collaboration.html | Daily agent reads command-center-state.json and uploads_manifest.csv
2026-05-31 | Cloud Platform | Created local-to-cloud plan for Pages Workers D1 R2 cron and webhooks | cloud_solution_plan.md | Turn plan into deployable Cloudflare scaffold after account/domain decisions
2026-05-31 | Cloud Platform | Added Cloudflare Worker API scaffold with D1 schema R2 uploads cron intake marker auth guard and local tests | ../../cloud/command-center-worker/README.md | Get Cloudflare account/domain/auth approval before deployment
2026-05-31 | Payments Licensing | Added desktop License & Billing panel plus license service and server device activation/offline grace metadata | ../../src/features/billing/LicensePanel.tsx | Replace alpha bearer token with customer-safe auth before paid beta
2026-05-31 | QA Test | Added license activation gate and verified clean temp build outside damaged synced node_modules | ../../docs/license-activation-gates.mjs | Keep build verification in temp workspace until synced dependencies are repaired
2026-05-31 | Release Ops | Added npm run build:clean so release verification runs outside the synced folder and includes license billing production cloud gates plus Windows unpacked build | ../../scripts/build-clean.ps1 | Use clean build output as the packaging baseline until code signing decision is made
2026-05-31 | Engineering Security | Checked npm audit in the clean build workspace: production dependencies are clear with --omit=dev | but Electron/build toolchain advisories remain a paid-beta blocker | ../../package.json
2026-05-31 | Engineering Security | Upgraded Electron/Vite/electron-builder toolchain and verified npm audit reports zero vulnerabilities in the clean build workspace | ../../package.json | Continue IPC high-impact action and consent security gates
2026-05-31 | Release Ops | Set internal app version and Windows product metadata for 0.1.0-alpha.1 clean build output | ../../electron-builder.json5 | Decide code signing or Microsoft Store path before paid beta
2026-05-31 | Payments Licensing | Replaced desktop alpha API token entry with checkout-session activation and device-scoped access tokens for license status and Customer Portal | ../../src/services/license.ts | Deploy billing backend and connect live Stripe webhooks
2026-05-31 | QA Test | Extended billing smoke and license activation gate to prove checkout-session claim and device-token license checks | ../../server/smoke-billing-server.mjs | Add live Stripe test-mode checkout after product price and webhook URL exist
2026-05-31 | Engineering Security | Added main-process paid feature gate for API swarm chat voice realtime screen capture computer control file/app control and developer terminal | ../../electron/licenseGate.ts | Finish typed IPC and high-impact approval gates
2026-05-31 | QA Test | Added test:paid-feature-gates and wired it into npm run build:clean so release builds fail if paid IPC enforcement is removed | ../../docs/paid-feature-gates.mjs | Add runtime unpaid-license denial test after installer test harness is stable
2026-05-31 | QA Test | Added runtime unpaid-license smoke test and clean build now proves computer control API swarm chat and screen capture are denied with NYRA_PRO_REQUIRED | ../../docs/paid-feature-runtime-smoke.mjs | Continue typed IPC and high-impact approval coverage
2026-05-31 | Command Center Intake | Created active daily Codex automation nyra-daily-command-center-build for saved dashboard answers uploads notes and Codex-owned build work | command-center-state.json | Use the Collaboration page as the handoff point for new decisions and files
2026-05-31 | Engineering Security | Added main-process high-impact approval gate with dialog approval audit log and NYRA_HIGH_IMPACT_APPROVAL_REQUIRED denial code | ../../electron/highImpactApproval.ts | Continue typed IPC hardening and first-run consent controls
2026-05-31 | QA Test | Added high-impact static and runtime smoke tests and fixed clean-build fail-fast behavior so release verification stops on failed npm or TypeScript commands | ../../scripts/build-clean.ps1 | Keep npm run build:clean as the authoritative release gate
2026-05-31 | Privacy Consent | Added first-run consent Settings Privacy & Consent export/delete local memory controls and NYRA_CONSENT_REQUIRED main-process enforcement | ../../src/services/privacyConsent.ts | Move privacy policy/EULA copy to final legal review
2026-05-31 | QA Test | Added privacy-consent static and runtime smoke tests proving paid IPC is denied without consent and allowed after consent is saved | ../../docs/privacy-consent-runtime-smoke.mjs | Continue typed IPC hardening and live billing deployment
2026-05-31 | Engineering Security | Added restricted preload IPC bridge with allowlisted invoke send listen channels store-key validation payload validation unsafe URL blocking and sanitized listener events | ../../electron/preload.ts | Move remaining launch risk to live billing deployment signing and legal decisions
2026-05-31 | QA Test | Added typed IPC static and runtime smoke tests and wired them into npm run build:clean | ../../docs/typed-ipc-runtime-smoke.mjs | Keep clean build as the release gate while live Stripe and signed release path are completed
2026-05-31 | Privacy Consent | Created privacy policy Terms EULA refund/cancellation security policy and legal review packet drafts matched to implemented consent paid-feature high-impact and typed IPC controls | ../../docs/policies/LEGAL_REVIEW_PACKET.md | Attorney review support inbox domain and public policy URLs remain before live payments
2026-05-31 | Business Legal | Generated NyrA_Legal_Review_Packet.docx for attorney/accountant review and wired policy drafts into command-center pages | ../../docs/policies/NyrA_Legal_Review_Packet.docx | User must choose legal entity/contact path and get policy review before publication
2026-05-31 | Product Program | Promoted the dashboard into a saveable collaboration workspace with handoff fields for business, pricing, support, domain, cloud, release channel, code signing, and Codex notes | index.html | Use Dashboard or Collaboration page as the user-to-Codex source of truth
2026-05-31 | Command Center Intake | Added Daily Agents page and runbook so automations know exactly what to read write and report every day | pages/agents.html | Daily agents should consume saved fields and continue unblocked P0 work
2026-05-31 | Cloud Platform | Added cloud handoff fields for account readiness admin email access model domain D1 and R2 status | pages/cloud.html | User must provide Cloudflare handoff details before deployment
2026-05-31 | Release Ops | Made app version mapping editable from the dashboard for beta distribution publisher mobile path and release notes readiness | pages/app-version.html | Keep desktop paid beta first while mapping mobile companion
2026-05-31 | QA Test | Added command-center collaboration smoke check and wired it into clean build verification | check_command_center_collaboration.mjs | Keep dashboard forms agent page and cloud/app-version pages from regressing
2026-05-31 | Marketing Campaign | Added generated launch site with product screenshots safe claims policy links and checkout readiness blockers | ../launch_site/index.html | Fill price hosted AI cap domain support and live Stripe details before public publishing
2026-05-31 | QA Test | Added launch-site regression check and wired launch-site generation into clean build verification | ../launch_site/check_launch_site.mjs | Keep unsafe claims fake checkout and missing policy links from regressing
2026-05-31 | Payments Licensing | Added standalone billing backend deploy pack with Node 24 package Dockerfile dockerignore deployment manifest and deployment checklist | ../../server/DEPLOYMENT_CHECKLIST.md | User must choose host domain secrets Customer Portal webhook and persistent storage before live deployment
2026-05-31 | QA Test | Added billing deployment readiness check and wired it into clean build verification | ../../docs/billing-deployment-readiness-check.mjs | Keep billing backend deploy artifacts route manifest secret list and Docker health check from regressing
2026-05-31 | QA Test | Added QA launch matrix with required clean-build gates targeted interaction smokes and live-rehearsal blockers | ../../docs/QA_LAUNCH_MATRIX.md | Keep every new P0 release gate mapped to a script and command-center page
2026-05-31 | QA Test | Added test:qa-launch-matrix and wired it into clean build verification | ../../docs/qa-launch-matrix-check.mjs | Keep package scripts build-clean coverage and command-center QA page from drifting
2026-05-31 | Support Ops | Added redacted support diagnostics export in Settings plus support operations runbook ticket categories refund workflow and support macros | pages/support.html | User still needs to create or confirm the support inbox and run a ticket roundtrip
2026-05-31 | QA Test | Added support readiness and support diagnostics runtime checks to the clean release gate | ../../docs/support-readiness-check.mjs | Keep diagnostics redaction support docs IPC wiring and command-center support page from regressing
2026-05-31 | Release Ops | Added release notes known issues rollback plan manifest generator SHA256SUMS generator and command-center release package page | pages/release-package.html | Use clean-build release evidence for internal QA until signing or store trust is decided
2026-05-31 | QA Test | Added release package verifier and wired release evidence generation into clean build | ../../docs/release-package-check.mjs | Keep release notes checksums manifest signing status and rollback evidence from drifting
2026-05-31 | Release Ops | Added app-version roadmap source doc dashboard board mobile companion boundary daily version-agent queue and clean-build regression gate | pages/app-version.html | Keep desktop paid beta first while mapping the future app companion without letting it outrank launch blockers
2026-05-31 | QA Test | Hardened command-center state writes with atomic replacement and a concurrency gate for overlapping intake and deployability agent runs | ../../docs/command-center-concurrency-check.mjs | Keep daily automations from corrupting shared dashboard state if schedules overlap
2026-05-31 | Visual Assets | Added visual asset inventory JSON CSV Markdown dashboard rows and final paid-beta screenshot approval gate | pages/visuals.html | Refresh screenshots after UI billing support consent and pricing flows freeze then record demo/ad videos
2026-05-31 | Cloud Platform | Added cloud command-center deploy preflight report JSON state block dashboard Cloud page panel and clean-build regression check | pages/cloud.html | Enter Cloudflare account admin email access model dashboard domain D1 ID Worker origin API URL and temporary token to clear deploy preflight blockers
2026-05-31 | Privacy Consent | Added AI provider data-flow draft for OpenAI Anthropic Google Gemini and xAI/Grok and wired it into policy readiness and command-center policy pages | ../../docs/policies/AI_PROVIDER_DATA_FLOW_DRAFT.md | Attorney must review provider/subprocessor language after final provider stack hosted AI cap support inbox and public URLs are chosen
2026-05-31 | Marketing Campaign | Added marketing campaign kit with beta invite email sequence social posts ad variants campaign calendar and video shot list | MARKETING_CAMPAIGN_KIT.md | Final recording and publication still wait on screenshots price cap domain policy URLs support and checkout
2026-05-31 | Command Center Intake | Added automation status inventory and regression gate so the Daily Agents page proves required Codex automations exist and are active | automation-status.json | Keep actual automation files aligned with command-center handoffs marketing cloud payments visuals and release gates
2026-06-01 | Command Center Intake | Updated required daily automation prompts and automation-status coverage so every scheduled NyrA agent must read Handoff Routing Rehearsal and Agent Dispatch Pack before choosing work | automation-status.json | Keep daily agents aligned with the dashboard collaboration path and department assignment board after each handoff scan
2026-06-01 | Command Center Intake | Added Handoff Delta Pack so the dashboard can show changed answers uploads and secret-presence status since the previous scan | handoff-delta-pack.json | Use Scan Handoffs after saving dashboard answers or loading files so daily agents can continue newly unblocked work
2026-05-31 | QA Test | Hardened generated command-center artifact readers with retry helpers for deployability intake cloud deploy visual and dashboard checks | ../../docs/test-read-utils.mjs | Keep overlapping daily-agent checks from failing on transient synced-file or atomic-rewrite reads
2026-06-01 | Command Center Intake | Updated required daily automation prompts and automation-status coverage so every scheduled NyrA agent regenerates and reads Public Launch Config before continuing paid-beta work | automation-status.json | Keep public domain support price cap policy URL and billing redirect handoffs wired into every daily agent queue
2026-06-01 | Command Center Intake | Preserved human requirement labels across handoff readiness rehearsal delta daily brief and agent dispatch outputs so departments see exact launch blockers instead of generic launch items | handoff-readiness.json | Keep every dashboard answer upload slot and daily-agent assignment traceable to a concrete requirement
2026-06-01 | Cloud Platform | Preserved launch requirement labels through the Cloudflare command-center Worker handoff scan and delta path so the future cloud source of truth keeps the same task context as the local dashboard | cloud/command-center-worker/src/index.mjs | Keep cloud state handoffs daily agent runs and dashboard sync aligned before moving the command center off local files
2026-06-01 | Cloud Platform | Added Cloud Bootstrap Pack with plan-only Cloudflare resource setup commands for D1 R2 Pages Workers secrets migrations deploys and first roundtrip checks | cloud-bootstrap-pack.json | Run Wrangler login then rerun Cloudflare discovery and bootstrap pack before approving any remote resource creation
2026-06-01 | Command Center Intake | Cleaned Agent Dispatch routing so collaboration workspace assignments require concrete dashboard fields or upload slots and the verifier rejects raw summary rows | agent-dispatch-pack.json | Keep Daily Agents page actionable as saved handoffs feed daily automation
2026-06-01 | Command Center Intake | Added Cloud Dashboard Ingest coverage to automation status and patched the 8:15 intake plus 8:30 daily build agents to run cloud handoff ingest before local refresh when cloud credentials are present | automation-status.json | Keep cloud dashboard entries flowing into local launch state before department agents choose daily work
2026-06-01 | Command Center Intake | Added a Daily Standup Fill-In Workbench with answer boxes upload slots and save/scan controls so the morning dashboard is directly actionable | pages/daily-standup.html | Use the Daily Standup page as the start-here collaboration surface before daily agents continue newly unblocked work
2026-06-01 | Command Center Intake | Required the central intake and daily build agents to publish refreshed local command-center state back to the cloud after ingest and rebuild work when cloud credentials are present | automation-status.json | Keep the cloud dashboard current with generated team updates instead of leaving it as a stale one-way handoff source
2026-06-01 | Payments Licensing | Aligned the billing backends with the no-trial first-launch rule so Stripe trialing subscriptions do not grant NyrA Pro and surfaced no-trial plus BYOK-later policy fields in payment/public launch dashboard packs | payment-launch-pack.json | Keep checkout and entitlement behavior matched to the public no-trial offer before live Stripe setup
2026-06-01 | Release Ops | Added a machine-readable release-candidate blocker queue and rendered it on the Release Package dashboard so daily agents and the command center share the same 9 blocked paid-beta checks | release-candidate-preflight.json | Use the Release Package page to review the paid-beta blockers before changing installer trust or customer distribution state
2026-06-09 | Command Center Intake | Reviewed Porter Labs LLC / porterlabz.com dashboard save and LLC upload evidence, marked the pending dashboard updates as agent-reviewed, and kept launch blockers routed without changing user-owned decisions | command-center-state.json | Continue daily intake until user handoffs or secret-store presence changes create newly ready work
2026-06-09 | Release Ops | Normalized command-center release version sources so the roadmap, queue text, release lane, and generated Pages artifact now point at 0.1.0-alpha.38 instead of stale alpha.1 copy | docs/launch_command_center/build_command_center.py | Keep release status derived from package/state versions so future alpha bumps do not leave stale command-center release text behind
2026-06-10 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.46, Android 0.1.0-alpha.46 versionCode 46, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-10 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.47, Android 0.1.0-alpha.47 versionCode 47, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-10 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.48, Android 0.1.0-alpha.48 versionCode 48, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-10 | Command Center Intake | Tightened agent-dispatch routing so broad team lanes inherit command-center profiles, ready Codex launch todos feed department assignments, and departments stop defaulting to passive watch states when actionable work exists | scripts/update-agent-dispatch-pack.mjs | Rebuild the command center after each routing change and confirm department assignments still point at relevant Codex-owned work
2026-06-10 | Command Center Intake | Ran the intake refresh against the launch command center; handoff delta found no new changes, source-of-truth routing stayed complete, and no real row became ready for Codex review | daily-standup.json | User handoffs, secret-store presence, Cloudflare setup, support proof, and release trust decisions remain the next blockers
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.48, Android 0.1.0-alpha.48 versionCode 48, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.49, Android 0.1.0-alpha.49 versionCode 49, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.50, Android 0.1.0-alpha.50 versionCode 50, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.51, Android 0.1.0-alpha.50 versionCode 50, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.51, Android 0.1.0-alpha.51 versionCode 51, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.52, Android 0.1.0-alpha.51 versionCode 51, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.52, Android 0.1.0-alpha.52 versionCode 52, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.53, Android 0.1.0-alpha.53 versionCode 53, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-11 | QA Test | Re-verified the hosted alpha bridge on the current 0.1.0-alpha.53 build: the trycloudflare URL, APK route, provider readiness, and support-log upload/list/readback are green, but this remains internal-alpha evidence only | docs/launch_command_center/hosted-alpha-status.json | Use npm run alpha:hosted:check before phone testing and do not treat hosted-alpha proof as a paid-beta bridge clearance
2026-06-11 | Command Center Intake | Reviewed the only ready-for-Codex handoff and kept the blocker routed: the saved phone self-test evidence still reports surface=web and passed=no, so the physical-phone bridge self-test is not cleared | docs/launch_command_center/mobile-phone-self-test-evidence.json | Keep pages/cloud-mobile-bridge.html, mobileBridge.lastPhoneSelfTest, phone-evidence, and the physical-phone rerun step visible until a real phone report is uploaded
2026-06-11T08:18:37-04:00 | Command Center Intake | Refreshed the launch command center intake queue and re-reviewed mobile-bridge-phone-self-test; the current saved evidence is still browser-preview/web-surface with passed=no, so Codex kept the P0 physical-phone gate blocked | docs/launch_command_center/mobile-phone-self-test-evidence.json | Run the self-test from a real phone against the deployed Worker, then rescan handoffs
2026-06-11T08:40:00-04:00 | Command Center Intake | Patched the intake and cloud handoff classifiers so failed phone self-test evidence stays visible as saved-but-failed review state and no longer appears as Ready for Codex review | scripts/command-center-intake-scan.mjs | Rebuild the command center and keep the cloud-mobile-bridge route pointed at a real physical-phone rerun until new proof arrives
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.54, Android 0.1.0-alpha.54 versionCode 54, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.55, Android 0.1.0-alpha.55 versionCode 55, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.56, Android 0.1.0-alpha.56 versionCode 56, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.57, Android 0.1.0-alpha.56 versionCode 56, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.57, Android 0.1.0-alpha.57 versionCode 57, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.58, Android 0.1.0-alpha.58 versionCode 58, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.59, Android 0.1.0-alpha.59 versionCode 59, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.60, Android 0.1.0-alpha.60 versionCode 60, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12T12:19:41.516Z | Command Center Intake | Refreshed the 2026-06-12 launch command center intake queue, marked the Codex-applied launch-defaults log item as reviewed, and confirmed there are no ready-for-Codex handoffs after the latest scan | docs/launch_command_center/command-center-state.json | Keep daily intake focused on new dashboard answers, uploads, app-version/payment/public/cloud changes, and secret-store presence; live-money remains blocked on user and secret-store handoffs
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.61, Android 0.1.0-alpha.61 versionCode 61, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12T12:32:17.339Z | Command Center Intake | Exposed inferred mobile-bridge bootstrap defaults in deployability and handoff readiness so Cloud Platform handoffs now show recommended R2 bucket names and APK R2 key without pretending the resources exist | scripts/bootstrap-mobile-bridge-cloud.mjs | Use the suggested values to create the real buckets and upload path, then save or verify them through cloud handoffs before deploy
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.62, Android 0.1.0-alpha.62 versionCode 62, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.63, Android 0.1.0-alpha.63 versionCode 63, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-12 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.64, Android 0.1.0-alpha.64 versionCode 64, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-13 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.64, Android 0.1.0-alpha.64 versionCode 64, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-13 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.65, Android 0.1.0-alpha.65 versionCode 65, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-13T08:19:13-04:00 | Command Center Intake | Refreshed the launch command center intake queue and re-reviewed mobile-bridge-phone-self-test; current evidence is NO_PHONE_SELF_TEST_LOG with passed=false, physicalPhone=false, and 0 phone-evidence files, so Codex kept the P0 physical-phone gate blocked | docs/launch_command_center/mobile-phone-self-test-evidence.json | Run the self-test from a real phone against the deployed Worker, upload or save the report to phone-evidence/mobileBridge.lastPhoneSelfTest, then rescan handoffs
2026-06-13T08:34:29-04:00 | Command Center Intake | Patched the local intake scanner and cloud command-center worker parity so NO_PHONE_SELF_TEST_LOG and missing phone-evidence no longer classify mobile-bridge-phone-self-test as Ready for Codex review | scripts/command-center-intake-scan.mjs | Regenerate the command-center packs and keep the physical-phone rerun route visible until a real phone report exists
2026-06-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.65, Android 0.1.0-alpha.65 versionCode 65, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.66, Android 0.1.0-alpha.66 versionCode 66, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.67, Android 0.1.0-alpha.67 versionCode 67, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.68, Android 0.1.0-alpha.68 versionCode 68, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.69, Android 0.1.0-alpha.69 versionCode 69, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.70, Android 0.1.0-alpha.70 versionCode 70, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.71, Android 0.1.0-alpha.71 versionCode 71, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-14T08:17:18-04:00 | Command Center Intake | Refreshed the launch command center intake queue; no rows are Ready for Codex review, Handoff Delta has no changed or newly ready rows, Source Of Truth has 0 missing routes, and deployability remains NO_GO_LIVE_MONEY. | docs/launch_command_center/daily-standup.json | User handoffs, secret-store presence, cloud resources, billing/support/legal evidence, signed release trust, and physical-phone self-test remain the next blockers to clear.
2026-06-14T12:34:00-04:00 | Command Center Intake | Regenerated the mobile-bridge cloud bootstrap report from the current Android manifest so the suggested hosted APK route now points at alpha/0.1.0-alpha.71/NyrA.apk instead of the stale alpha.65 key across deployability, handoff, and source-of-truth packs. | docs/launch_command_center/mobile-bridge-cloud-bootstrap.json | Keep the cloud-mobile-bridge APK handoff visible until the real R2 upload path is saved or a stable hosted APK URL is verified.
2026-06-15 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.71, Android 0.1.0-alpha.71 versionCode 71, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-15 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.72, Android 0.1.0-alpha.72 versionCode 72, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-15T08:19:13-04:00 | Command Center Intake | Refreshed the launch command center intake queue; no rows are Ready for Codex review, Handoff Delta has no changed or newly ready rows, Source Of Truth has 0 missing routes, and deployability remains NO_GO_LIVE_MONEY for 0.1.0-alpha.72. | docs/launch_command_center/daily-standup.json | User handoffs, secret-store presence, cloud resources, billing/support/legal evidence, signed release trust, final screenshots, and physical-phone self-test remain the next blockers to clear.
2026-06-15T12:45:00-04:00 | Visual Assets | Updated the visual inventory generator and regression checks so Android screenshot routing now prefers the latest available alpha71 launch and panel captures instead of hardcoded alpha46 evidence while keeping final screenshot approval blocked and stale-version reporting honest for 0.1.0-alpha.72 | scripts/update-visual-assets.mjs | Capture alpha72 Android screenshots and final paid-beta desktop/support visuals after the UI, billing, support, and consent flows are frozen
2026-06-16 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.72, Android 0.1.0-alpha.72 versionCode 72, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-16 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.73, Android 0.1.0-alpha.73 versionCode 73, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-16 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.74, Android 0.1.0-alpha.74 versionCode 74, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-16 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.75, Android 0.1.0-alpha.75 versionCode 75, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-16 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-17 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-18 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-06-20 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-01 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-02 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-03 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-04 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-05 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-06 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-07 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-08 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-09 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-10 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-14 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-15 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.76, Android 0.1.0-alpha.76 versionCode 76, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-15 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.79, Android 0.1.0-alpha.79 versionCode 79, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-15 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.80, Android 0.1.0-alpha.80 versionCode 80, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-15 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.81, Android 0.1.0-alpha.81 versionCode 81, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-15 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.83, Android 0.1.0-alpha.83 versionCode 83, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-16 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.83, Android 0.1.0-alpha.83 versionCode 83, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-17 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.83, Android 0.1.0-alpha.83 versionCode 83, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center
2026-07-18 | Release Ops | Synced command-center release metadata to 0.1.0-alpha.83, Android 0.1.0-alpha.83 versionCode 83, and current release evidence so daily queues stop drifting behind the actual alpha build | scripts/sync-command-center-release-metadata.mjs | Run npm run release:metadata:sync after any version bump or release artifact refresh before trusting the command center

## Sources
Source | Use | URL
SC Business One Stop | Starting a business hub and startup wizard | https://scbos.sc.gov/
SC Secretary of State Business Entities | Business entity search and online filings | https://businessfilings.sc.gov/
SC DOR Business Tax Registration | MyDORWAY business tax application and Retail License | https://dor.sc.gov/tax/registration
SC DOR Retail License | Retail License fee and sales/use tax licensing notes | https://dor.sc.gov/index.php/businesses/apply-business-tax-account/licensing-retail-license
IRS EIN Online | Free EIN application directly from IRS | https://www.irs.gov/businesses/small-businesses-self-employed/apply-for-an-employer-identification-number-ein-online
FinCEN BOI FAQ | Domestic entities currently exempt from BOI reporting under interim final rule | https://www.fincen.gov/index.php/boi-faqs
USPTO Trademark Search | Federal trademark search before name/brand filing | https://www.uspto.gov/trademarks/search
US Copyright Office Fees | Software/content registration fee reference | https://www.copyright.gov/about/fees.html
Stripe Pricing | US online card transaction fee baseline | https://stripe.com/us/pricing
Stripe Checkout | Hosted checkout for payments/subscriptions | https://docs.stripe.com/payments/checkout
Stripe Subscriptions | Subscription design and billing architecture | https://docs.stripe.com/billing/subscriptions/design-an-integration
Stripe Customer Portal | Self-service cancellation/invoices/payment methods | https://docs.stripe.com/customer-management/integrate-customer-portal
Stripe Go-Live Checklist | Live payment readiness checklist | https://docs.stripe.com/get-started/checklist/go-live
Stripe Test Mode | Test mode and sandbox integration rehearsal | https://docs.stripe.com/test-mode
Stripe Subscription Webhooks | Required asynchronous subscription lifecycle events | https://docs.stripe.com/billing/subscriptions/webhooks
FTC Click to Cancel | Subscription cancellation and consent expectations | https://www.ftc.gov/business-guidance/blog/2024/10/click-cancel-ftcs-amended-negative-option-rule-what-it-means-your-business
FTC Start with Security | Security/privacy expectations for businesses | https://www.ftc.gov/business-guidance/resources/start-security-guide-business
FTC Protecting Personal Information | Practical security safeguards and incident planning | https://www.ftc.gov/business-guidance/resources/protecting-personal-information-guide-business
FTC Biometric Policy Statement | Voice/biometric claims and consent risk | https://www.ftc.gov/legal-library/browse/policy-statement-federal-trade-commission-biometric-information-section-5-federal-trade-commission
OpenAI Data Controls | API data retention and store parameter behavior | https://platform.openai.com/docs/guides/your-data
Anthropic Organization Data Retention | Commercial API input/output retention and exceptions | https://privacy.claude.com/en/articles/7996866-how-long-do-you-store-my-organization-s-data
Anthropic Processor Controller FAQ | Commercial customer data processing and model training posture | https://support.claude.com/en/articles/9267385-does-anthropic-act-as-a-data-processor-or-controller
Google Gemini API Data Logging | Logging retention and opt-in model-improvement sharing controls | https://ai.google.dev/gemini-api/docs/logs-policy
xAI API Security FAQ | API training posture temporary retention and ZDR notes | https://docs.x.ai/developers/faq/security
OpenAI API Pricing | Hosted AI token cost baseline for pricing model | https://platform.openai.com/docs/pricing/
SC Data Breach Notification | South Carolina personal identifying information breach notification reference | https://law.justia.com/codes/south-carolina/title-39/chapter-1/section-39-1-90/
Stripe Refunds Support | Customer refund workflow reference | https://support.stripe.com/questions/how-to-refund-a-customer
Microsoft Partner Center Signup | Windows developer account onboarding | https://learn.microsoft.com/en-us/windows/apps/get-started/sign-up
Microsoft SmartScreen | Windows app reputation and signing trust path | https://learn.microsoft.com/en-us/windows/apps/package-and-deploy/smartscreen-reputation
Microsoft SignTool | Windows signing and verification command reference | https://learn.microsoft.com/en-us/windows/win32/seccrypto/signtool
Microsoft MSIX Package Signing | Windows app package signing workflow | https://learn.microsoft.com/en-us/windows/msix/package/sign-app-package-using-signtool
Microsoft Package Identity | Package identity requirements for Windows apps | https://learn.microsoft.com/en-us/windows/apps/desktop/modernize/package-identity-overview
Microsoft Store Submission API | Store submission path and MSI/EXE notes | https://learn.microsoft.com/en-us/windows/apps/publish/store-submission-api
Electron Builder Windows Code Signing | Electron Windows signing configuration reference | https://www.electron.build/docs/tutorials/code-signing-windows-apps-on-unix/
SSL.com OV Code Signing | Code signing certificate price reference | https://www.ssl.com/products/software-integrity/code-signing/ov/
Google Workspace Pricing | Custom business email pricing reference | https://workspace.google.com/pricing.html
Cloudflare Registrar | At-cost domain registration reference | https://www.cloudflare.com/products/registrar/
Cloudflare Wrangler Configuration | Worker configuration D1/R2 bindings and JSONC config guidance | https://developers.cloudflare.com/workers/wrangler/configuration/
Cloudflare Cron Triggers | Scheduled Worker handler and cron trigger configuration | https://developers.cloudflare.com/workers/configuration/cron-triggers/
Cloudflare Workers Best Practices | Worker compatibility secrets request limits Web Crypto and deployment hardening guidance | https://developers.cloudflare.com/workers/best-practices/workers-best-practices/
Cloudflare D1 Worker Binding API | D1 database binding prepare first run and batch API guidance for Workers | https://developers.cloudflare.com/d1/worker-api/
Cloudflare Workers Secrets | Store Worker secrets outside source and config | https://developers.cloudflare.com/workers/configuration/secrets/
Cloudflare Workers Web Crypto | Use crypto.randomUUID digest and SubtleCrypto APIs in Workers | https://developers.cloudflare.com/workers/runtime-apis/web-crypto/

## Handoffs
Id | Requirement | Lane | Owner | QueueStatus | DashboardPage | DashboardField | CurrentValue | ValueStatus | UploadSlot | FilesInSlot | NextStep
legal-review | Attorney/accountant review approved for paid beta | Business Legal | User | Waiting on user | pages/billing-rehearsal.html | billingRehearsal.attorneyReviewStatus | Not approved | Needs input | legal-review | 0 | Mark Approved only after attorney/accountant review clears paid beta.
billing-live-mode | Billing rehearsal mode set to live for final money preflight | Payments Licensing | User + Codex | User + Codex gated | pages/billing-rehearsal.html | billingRehearsal.mode | test | Needs input | stripe-screenshots | 0 | Switch to live only after test-mode rehearsal, legal, support, and Stripe gates pass.
signed-release | Paid beta installer is signed or store-trusted | Release Ops | User + Codex | User + Codex gated | pages/release-package.html | releasePackage.signingStatus | Unsigned internal alpha evidence only | Saved | code-signing | 0 | Upload or generate signed/store-trusted release evidence after the signing path is chosen.

## Status Summary
Status | Count
Active
Blocked on entity/EIN
Blocked on formation
Blocked on physical phone proof
Domain saved
In progress
Not started
Open
Ready
SC LLC selected
Waiting on tax/pricing